Schedule G

Tasmania

Project agreement for small business regulatory reform

# Part 1 – Preliminaries

* 1. This Schedule has been developed in accordance with clause 10 of the Agreement.
  2. This Schedule will commence as soon as it is agreed between the Commonwealth and Tasmania and expire on 30 June 2021 or on completion of agreed projects, including final performance reporting and processing of final payments against milestones.

# Part 2 – Financial Arrangements

* 1. The Commonwealth will provide an estimated financial contribution to Tasmania of up to $6.4 million in respect of this Agreement. All payments are exclusive of GST.

**Table 1: Estimated financial contributions**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **($ million)** | 2018-19 | 2019-20 | 2020-21 | Total |
| **Estimated total budget** | **2.0** | **1.1** | **3.3** | **6.4** |
| Less estimated National Partnership payment | 2.0 | 1.1 | 3.3 | 6.4 |
| Balance of non-Commonwealth contributions | 0.0 | 0.0 | 0.0 | 0.0 |

# Part 3 – Project Milestones, Reporting and Payments

* 1. Tasmania will deliver the following projects:

1. Project 1 – *Water and sewerage infrastructure spatial data mapping.* The project will expand the scope of the Planning and Building Portal to deliver water infrastructure spatial data in a digital format to assist small businesses undertaking development projects. Estimated financial contributions to Project 1 are as follows:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **($ million)** | 2018-19 | 2019-20 | 2020-21 | Total |
| **Estimated total budget** | **0.4** | **0.3** | **0.3** | **1.0** |
| Less estimated National Partnership payment | 0.4 | 0.3 | 0.3 | 1.0 |
| Balance of non-Commonwealth contributions | 0.0 | 0.0 | 0.0 | 0.0 |

1. Project 2 – *Bushfire risk spatial data mapping.* The project will expand the scope of the Planning and Building Portal to deliver bushfire risk spatial data in a digital format to assist small businesses undertaking development projects.Estimated financial contributions to Project 2 are as follows:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **($ million)** | 2018-19 | 2019-20 | 2020-21 | Total |
| **Estimated total budget** | **0.6** | **0.3** | **0.1** | **1.0** |
| Less estimated National Partnership payment | 0.6 | 0.3 | 0.1 | 1.0 |
| Balance of non-Commonwealth contributions | 0.0 | 0.0 | 0.0 | 0.0 |

1. Project 3 – *Environmental, public health & heritage application assessments.* The project will expand the scope of the Planning and Building Portal to deliver state-wide online processes for environmental permits, heritage assessments, and food permits such as café, vineyards and other food venues. The project will assist small businesses who require these permits and who seek to expand their operations. Estimated financial contributions to Project 3 are as follows:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **($ million)** | 2018-19 | 2019-20 | 2020-21 | Total |
| **Estimated total budget** | **0.0** | **0.5** | **2.5** | **3.0** |
| Less estimated National Partnership payment | 0.0 | 0.5 | 2.5 | 3.0 |
| Balance of non-Commonwealth contributions | 0.0 | 0.0 | 0.0 | 0.0 |

1. Project 4 – *Automation of licence verification*. The project will create an interface that will integrate licencing, registration and related systems into the Planning and Building Portal to assist businesses required to manually check the licencing conditions of practitioners involved with a building and planning process. Estimated financial contributions to Project 4 are as follows:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **($ million)** | 2018-19 | 2019-20 | 2020-21 | Total |
| **Estimated total budget** | **1.0** | **0.0** | **0.4** | **1.4** |
| Less estimated National Partnership payment | 1.0 | 0.0 | 0.4 | 1.4 |
| Balance of non-Commonwealth contributions | 0.0 | 0.0 | 0.0 | 0.0 |

* 1. Table 2 summarises the milestones for the projects, their relationship to the outputs, expected completion dates, relevant reporting dates and expected payments to be made.

**Table 2: Milestones, reporting and payment summary**

|  |  |  |  |
| --- | --- | --- | --- |
| 2018-19 | | | |
| Output | Milestones | Report due | Payment |
| *Project 1 – Water and Sewerage spatial data mapping* | Achievement of scheduled progress according to the proposal summary such that practitioners assisting small businesses to meet regulatory requirements can access sewerage and water infrastructure via the Land Information System (LIST) for all properties in at least 30 per cent of Tasmanian LGAs. These practitioners will be able to unambiguously determine which (if any) further approvals from TasWater are required. | April 2019 | $0.4 million |
| *Project 2 – Bushfire risk spatial data mapping* | Achievement of scheduled progress according to the proposal summary such that businesses advising developers on bushfire risk management can access spatial data mapping of bushfire risk to unambiguously determine the appropriate regulatory obligations for all properties in Tasmania, including whether a Bushfire Hazard Management Plan will be required. This data will be made available through the Tasmanian Fire Service (TFS). | April 2019 | $0.6 million |
| *Project 4 – Automation of licence verification* | Achievement of scheduled progress according to the proposal summary such that businesses can search for, and verify the licence and licence conditions of all people working for them on a building site or project through the Occupational Licensing and Compliance (OLAC system). | April 2019 | $1.0 million |

|  |  |  |  |
| --- | --- | --- | --- |
| 2019-20 | | | |
| Output | Milestones | Report due | Payment |
| *Project 1 – Water and Sewerage spatial data mapping* | Achievement of scheduled progress according to the proposal summary such that practitioners assisting small businesses to meet regulatory requirements can access sewerage and water infrastructure via the LIST for all properties in at least 60 per cent of Tasmanian LGAs. These practitioners will be able to unambiguously determine any further approvals from TasWater required. | April 2020 | $ 0.3 million |
| *Project 2 – Bushfire risk spatial data mapping* | Achievement of scheduled progress according to the proposal summary such that all landowners and developers can identify the need for a Bushfire Hazard Management Plan through bushfire risk spatial data integrated with the title search process of the Land Information System (LIST). | April 2020 | $ 0.3 million |
| *Project 3 – Environmental public health & heritage application assessments* | Achievement of scheduled progress detailed in the proposal summary such that businesses are able to complete digital applications for environmental, public health and heritage approval. | April 2020 | $0.5 million |

|  |  |  |  |
| --- | --- | --- | --- |
| 2020-21 | | | |
| Output | Milestones | Report due | Payment |
| *Project 1 – Water and Sewerage spatial data mapping* | Completion of the project in accordance with the proposal summary including: providing free and open access to spatial data for sewerage and water infrastructure for all of Tasmania through the online Planning and Building portal. | April 2021 | $0.3 million |
| *Project 2 – Bushfire risk spatial data mapping* | Completion of the project in accordance with the proposal summary including: providing free and open access to spatial data for bushfire risk through the online Planning and Building portal. | April 2021 | $ 0.1 million |
| *Project 3 – Environmental public health & heritage application assessments* | Completion of project in accordance with the proposal summary, including: integrating environmental, public health and heritage applications with broader development and planning applications on the Planning and Building portal. | April 2021 | $2.5 million |
| *Project 4 – Automation of licence verification* | Completion of project in accordance with the proposal summary, including: integrating licencing compliance systems with the Planning and Building Portal to automate the verification of licenses. | April 2021 | $0.4 million |

# Part 4: Sign Off

* 1. The Parties have confirmed their commitment to this agreement as follows:

**Signed** *for and on behalf of the Commonwealth of Australia by*

-----------------------------------------------------

The Honourable Josh Frydenberg MP

Treasurer

[Day] [Month] 2018

**Signed** *for and on behalf of Tasmania by*

-----------------------------------------------------

The Honourable Peter Gutwein MP

Treasurer

[Day] [Month] 2018