Homelessness National Partnership

Implementation Plan for Tasmania

July 2009 – June 2013

Contents:

Introduction	3

Whole of Government Commitment	4

Social Inclusion	4

State Homelessness Plan	4

Agency Commitment	5

Reforms in the Department of Health and Human Services (DHHS)	5

Social Housing and Specialist Homelessness Services	7

Environmental Scan	10

Core Output: A Place To Call Home (APTCH)	15

Initiative 1: Same House Different Landlord Program	15

Core Output: Street to home initiatives for chronic homeless people	17

Initiative 2: Dedicated homelessness facilities x 5	17

Core Output: Support for private and public tenants to help sustain their tenancies.	19

Initiative 3: Specialist intervention tenancy services	25

Discretionary Output: Improvement in service coordination and provision.	26

Initiative 4: Improvements in Service Coordination and Provision	27

Discretionary Output: National, State and rural (including remote) homelessness action plans.	28

Initiative 5: State Homelessness Plan	28

Discretionary Output: Workforce development and career progression for workers in homelessness services.	30

Initiative 6: Workforce capacity audit and development plan	30

Remaining Discretionary Outputs:	31

Figure 1: Current SAAP system and pathways to housing options	9

Figure 2: System Expansion and Improvement	14

Table 1: Homelessness Implementation Plan Initiatives.	13

##### Preamble

This document outlines Tasmanian specific actions and new initiatives for the Homelessness Implementation Plan over the five year period until June 2013.  Priorities may be adjusted in light of the State Homelessness Plan which is currently being developed in consultation with key stakeholders and the Tasmanian community.  Further refinements may also be required as initiatives are implemented and intended reforms are achieved and evaluated.  The initiatives documented here respond to the four core outputs from the Homelessness National Partnership Agreement and six of the discretionary output areas 17 (d), (e), (g), (h), (i) and (l). This is to ensure our effort and energy is not spread too thinly and we can consolidate areas of greatest priority.

# Introduction

Homelessness and social housing are major priorities for the Tasmanian Government.  The Government has committed to establishing a benchmark figure for primary homelessness in Tasmania and halving the number of people who are sleeping rough by 2010.  An internationally renowned housing expert Dr Rosanne Haggerty was engaged to provide advice to Government on new ways to reduce homelessness and boost Tasmania’s public housing stock.  As a result the Government has committed an additional $60 million and established a Housing Innovations Unit with the Department of Health and Human Services (DHHS) to address supply issues.  The Government has also committed to developing a State Homelessness Plan to reduce homelessness in Tasmania.

This policy directive and associated funding will significantly build on Tasmania’s progressive homelessness service system which has undergone substantial reform in recent years.  However, notable pressure points remain within the system; these pressure points are consistent with those identified in the White Paper on homelessness The Road Home.

The Tasmanian Government is focused on achieving a ‘clever, kind and connected’ community.  A major driver for Government is to improve the coordination and integration of services at a local level.  Initiatives to achieve a more connected service system include:

reform of the human services system through the introduction of a Gateway Model that brings family support, child protection, youth justice and disability services together through a lead non-government organisation at a local level;

the creation of eight Child and Family Centres providing comprehensive, integrated programs that combine parent support, nurturing, care, nutrition, and stimulation in the early childhood years at the local level;

introduction of training colleges, known as Polytechnics;

development of Integrated Care Centres to bring together primary health services and step down acute services in dispersed areas;

increased funding to mental health and drug and alcohol services to increase service capacity, integration and partnerships with the community sector in order to provide expanded community based clinical recovery, rehabilitation and supported accommodation; and

the establishment of a Social Inclusion Unit within a central agency, the Department of Premier and Cabinet, appointment of  a Commissioner for Social Inclusion, and the development of a Social Inclusion Strategy.

Concerning homelessness and social housing, priorities for Tasmania are to increase the supply of affordable accommodation and expand the range of homelessness services including the provision of targeted specialist support.  This targeted specialist support will assist the most vulnerable transition into sustainable long term housing.  Another priority is to build an integrated service system where support services are linked to ensure tenancies are able to be maintained and housing products are co-ordinated to achieve seamless pathways through the range of social housing options.  These priorities are reflected in the six key initiatives identified in this Implementation Plan.  To support this activity, there is also a focus on increasing sector capacity via workforce strategies, systems and infrastructure that support integrated service delivery.

This work will be guided by the development of the State Homelessness Plan to ensure a whole of government, whole of community response to homelessness within a social inclusion framework.

## Whole of Government Commitment

### Social Inclusion

Social inclusion is a key component of the Tasmanian Government’s commitment to building a clever, kind and connected Tasmania; as such the development of a Social Inclusion Strategy is a priority.  The Strategy is intended to ensure all Tasmanians have the opportunity to participate in social, economic and civic life and be supported by a system that helps people to access support services, education and job opportunities, as well as social and community networks.

The Social Inclusion Unit was established in 2008 within the Department of Premier and Cabinet to ensure a whole of government approach.  The Unit is currently developing the Social Inclusion Strategy and the State Homelessness Plan, the latter in partnership with Housing Tasmania.  It is envisaged that the Social Inclusion Strategy will be the overarching policy position under which the State Homelessness Plan will be located.

### State Homelessness Plan

Reducing the number of people who are experiencing or are at risk of homelessness is a major state priority.  The State Homelessness Plan will drive additional effort on reducing homelessness.  A key tenet of the Plan is that homelessness is a whole of government and whole of community issue.  The Chamberlain and MacKenzie 2006 Counting the Homeless: Tasmania report state that the total number of homeless people in Tasmania in 2006 was 2,507.  The number of primary homeless or rough sleepers is cited as 385.  Halving this figure results in a target of 192.5, this has been rounded up to 193.

Achieving the State goal of halving the benchmark number of 385 rough sleepers to 193 by 2010 will only be possible if all specialist and mainstream systems work together and service systems make homelessness a priority.

The State Homelessness Plan will include initiatives that seek to lever activity by mainstream services in identifying and responding effectively to individual and structural causes of homelessness.  It is anticipated that additional activity above and beyond the National Affordable Housing Agreement (NAHA) will be facilitated by the Social Inclusion Unit and Housing Tasmania to complement the NAHA and support local initiatives.  The State Homelessness Plan will also encompass the effort under the NAHA and associated National Partnership Agreements (NPAs) on Homelessness, Social Housing and Indigenous Housing, and the Nation Building and Jobs NPA.

##### Governance

A formal Homelessness Steering Committee has been established co-chaired by the Director of the Social Inclusion Unit and the Director of Housing Tasmania.  Two Reference Groups, one for key peaks and non-government organisations and a second for relevant government departments sit under the Steering Committee.  The Steering Committee with input from the two Reference Groups will direct the development of policies, strategies, and monitor and report on effort to address homelessness at a state, regional and national level. This arrangement ensures state based effort and that directed by the national agreements are efficient, linked and complementary.

## Agency Commitment

### Reforms in the Department of Health and Human Services (DHHS)

The current Agency direction supports improved client pathways and service integration.  Major reform is underway to amalgamate Primary Health and Acute Care Services including rural hospitals at a local level to enable better integration of services.  Similarly, there is significant work under way to reform a number of Human Services’ business units in order to support high quality services and effective outcomes for children, youth, families and people with disabilities.  Key priorities in the Agency’s Strategic Plan include:

easier access points of entry to government and non government services;

less structural boundaries and gate-keeping;

decision making at the right level involving the right people at the right time;

more tailored packages of services to individual needs;

more integration and co-ordination between services;

fewer layers to services and decision making processes; and

more capacity to pool funding and combine effort.

##### Disability, Child, Youth and Family Services (DCYFS)

A “Gateway” service will be established in each of the four Disability, Child, Youth and Family Services Areas (DCYFS) in the state. The Gateway will provide visible community intake and entry points and establish a clear referral pathway for children, young people, families, and people with a disability.  The Gateway will also provide information and advice to professionals such as teachers, community agencies and general practitioners in relation to family support and specialist disability services in order to refer families to appropriate services.  The restructured DCYFS is complemented by increased investment in Intensive Family Support Services and a review of Out of Home Care provision.

The inclusion of specialist homelessness services in the Gateway model is an opportunity in the reform process that will be examined.  As a starting point clear referral pathways will be established between Gateway and Specialist Homeless Services.

##### Mental Health

In Tasmania, 2004 was a watershed year for mental health services in the State.  Three major reviews: Bridging the Gap; the Thin Ice Report from Anglicare; and the Health Complaints Commission review of Ward 1E (Launceston General Hospital inpatient ward) made recommendations about the delivery of services to Tasmanians who experience mental illness and disorders.  As a result of those reviews, the Tasmanian Government committed $47 million over four years to improving mental health services.  This is the largest ever funding increase in the 170 year history of Tasmania’s mental health service, and has taken Tasmania to a new threshold of service to contemporary community based services.

The package of reforms expands the provision of services, particularly through partnerships. These partnerships are amplified through the engagement of the non-government sector to work with the State Government’s Mental Health Services to provide earlier access to more effective treatment for more Tasmanians, no matter where they live.

The injection of additional funding has enabled growth in clinical mainstream mental health services, particularly:

community based mental health services;

development of assertive case management; and

partnerships with the community sector to provide supported accommodation, recovery and rehabilitation.

The State Homelessness Plan, specialist intervention tenancy services and service coordination and improvement initiatives identified in this Implementation Plan will link with the increased effort in mainstream Mental Health Services.

##### Alcohol and Drug Services

As part of the 2008-09 Budget, the Tasmanian Government has committed $17.1 million over four years to the development of alcohol, tobacco and other drug services in Tasmania.  Approximately half this investment will be in the community sector.  This is the single biggest investment ever made in the sector in this State and highlights the Government’s commitment to improving services for people with problem alcohol and drug use.

A tiered service delivery model has been adopted to provide clear direction on responsibility for service response across the full continuum of alcohol, tobacco and other drug support and interventions.  The model recognises the importance of integration and collaboration between the specialist alcohol, tobacco and other drug services, other health and human service providers, private and community sector organisations.

Once again the State Homelessness Plan, specialist intervention tenancy services and coordination and improvement initiatives within this Implementation Plan will see specialist homelessness services better integrated with this increased effort in mainstream Alcohol and Drug Services.

### Social Housing and Specialist Homelessness Services

##### Housing Tasmania

Housing Tasmania is located within Human Services, which is within the broader DHHS. Human Services includes: Housing Tasmania, Family Services, Child Protection, Youth Justice and Disability Support services.  Homelessness policy is located in Housing Tasmania.  Homelessness policy and former SAAP program administration were co-located in Housing Tasmania in 2006; this move has provided opportunities for better policy and program integration.  The size and scale of Tasmania and the fact that Housing Tasmania is located within this broader health and human services framework also provides significant opportunities for ensuring mainstream services are more closely engaged with the provision of support and services to people who are homeless or at risk of homelessness. Housing Tasmania administers a range of housing products to support low income Tasmanians including assistance into private rental and home ownership.

Within Tasmania’s social housing system, public and Aboriginal housing is highly targeted to high and complex need clients.  Significant reform was implemented within Housing Tasmania’s service delivery arm in 2008 to improve the identification of need and the coordination of support to public housing tenants.  The new vision for public and Aboriginal housing is a service system that is flexible and responsive to client needs, with staff that are trained and supported to deliver a consistent and high quality service. Despite these changes managing high need and complex tenancies remains a pressure point within the public and Aboriginal housing portfolio.

##### Current specialist homelessness services

Specialist homelessness services are now funded under the NAHA.  The initiatives outlined in this Plan are in addition to the existing Commonwealth and state funded effort on specialist homelessness services under the NAHA.  Funding allocated to specialist homelessness services in the 2009-10 financial year will be in excess of $16.5 million.

There are thirty-four formerly SAAP funded services in Tasmania.  During the SAAP IV Agreement (2000–2005) Tasmania completed a restructure of the entire homelessness service system within the state.  The new service system is based on the Integrated Continuum of Support (ICOS) model, featuring:

an integrated service system;

a clearly defined set of service types detailing service specifications and functions;

the separation of support from the provision of accommodation enabling support to be flexible and follow the client; and

an equitable funding rationale based on input unit-costs and proportional regional funding based on regional populations.

The integration of services within each region has been crucial in providing increased flexibility and better services to clients.  Rather than each service trying to provide the full range of services itself, the modular nature of the model requires services to work collaboratively in providing joint support for clients.  Different services focus on different aspects of the client’s needs and support can follow the client wherever they are located.

An integral part of the homelessness service system reform was the introduction of the Client Brokerage Fund Model.  Brokerage provides an increased level of flexibility and innovation in the provision of support.  This also assists pressure on the existing network of homeless shelters.

Usage of the Brokerage funds generally falls into one of the following three categories:

purchase of immediate accommodation in the private market;

purchase of specialist support as needed, such as counselling services; and

one-off purchase of material aid to eliminate barriers to a client’s independence.

For a high level snap shot of the current system see Figure 1: Current SAAP system and pathways to housing options.

Figure 1: Current SAAP system and pathways to housing options

### Environmental Scan

An environmental scan was conducted as part of the planning and development of the Homelessness Implementation Plan, this comprised:

mapping homelessness services provided by the Australian and state governments, and the non-government sector;

collation of all recommendations provided to the National Youth Commission Inquiry into Youth Homelessness, the Homelessness Green Paper consultation by state government, the non-government sector and private organisations;

recommendations of the Rosanne Haggerty report Ending Homelessness In Tasmania, 2008; and

a consultation meeting with key non-government organisations and peaks.

An analysis of the information collated revealed pressure points and gaps in the specialist homelessness service system and in the provision of mainstream services.  The six initiatives outlined below detail how these pressure points and gaps are to be addressed.

##### Overview of Tasmania’s Homelessness Implementation Plan (IP)

Tasmania proposes six initiatives under the Homelessness IP:

- Introduction of a Same House Different Landlord program

- Dedicated homelessness facilities (utilises $10million APTCH funding)

- Specialist intervention tenancy services

- Service coordination and improvement initiatives

- State Homelessness Plan

- Workforce capacity audit and development plan

Four of the initiatives will address multiple Homelessness National Partnership Outputs.  The initiatives, a brief description and the outputs to which they relate are outlined in Table 1 below.

These initiatives address key state (and Australian Government) priorities of:

increasing the supply of accommodation for those experiencing or at risk of homelessness;

expanding specialist services for hard to reach client groups;

improving overall service co-ordination and provision; and

conducting a specialist homelessness service work force audit and prepare a development plan.

Initiative 1, Introduction of Same House Different Landlord Program which will enable people experiencing homelessness to move directly into accommodation that can ultimately become their long term housing option.  Tenants will be linked in with support for the duration of their need.  This initiative will prevent people experiencing repeat episodes of homelessness through enabling them to remain in the property at the end of the support period once their tenancy is stabilised.  This initiative will be supported by the specialist intervention tenancy services in initiative 3.  It will be rolled out in two phases.  Phase 1 will see services established in the North and South East Areas in 2009-10.  Phase 2 will see the roll out of the program state wide with the establishment of services in the Northwest and Southwest Areas in 2010-11.  Funding allocated to this initiative is to support the tenancy management model being proposed, that is, management of a pool of properties, replenished from public housing and potentially other social housing stock, to be allocated to priority target groups.  For further details see page 15.

Initiative 2, Dedicated homelessness facilities: Tasmania will acquire five specific purpose facilities for homeless people over the next two years, two in Hobart and two in Launceston and one in Devonport. The Liverpool St facility within the Hobart CBD will be managed by Common Ground Tasmania Inc. which has been established to support the Tasmanian Government’s goals in relation to homelessness.  The APTCH election commitment comprising the Commonwealth’s $5 million and the State’s $5 million matching, will be utilised within Initiative 2.  For further details see page 17.

Initiative 3, New specialist intervention tenancy services will provide a multidisciplinary team of specialist tenancy support and professional practitioners who will provide assistance to people:

- at key transition points where they are at high risk of homelessness including to young people leaving care and protection or youth justice, and adults leaving correctional facilities;

- with multiple needs who are homelessness or at risk;

- who experience multiple episodes or extended periods of homelessness (the chronic homeless population); and

- who are at risk of tenancy failure in public or private housing.

The implementation of initiative 3 will be aligned to the implementation of initiative 1.  For further details see page 25.

Initiative 4, Improvements in service coordination and provision will focus on improving service coordination and engagement of mainstream services to ensure a seamless pathway through social housing.  This project aims to create an evidence based best practice model through the development of:

- improved quality and standards;

- improve performance information;

- linkages with mainstream services;

- integration with state Health and Human Services reforms;

- a common assessment framework and practices; and

- a property register and allocations framework.

For further details see page 27.

Initiative 5, State Homelessness Plan is being developed by the State Government and funds identified under this initiative will provide some capacity (albeit limited) to resource planning, action and change management at a local and regional level.  Importantly the development of the State Homelessness Plan is being led by the Social Inclusion Unit within the Tasmanian Department of Premier and Cabinet.  The Plan names homelessness as a whole-of-community and whole-of-government responsibility and aims to improve early identification and referral of people at risk.  For further details see page 28.

Initiative 6, Workforce capacity audit and development plan will focus on identifying the training and development needs of the sector and will aim to put in place strategies that foster continuous quality improvement in the context of the changing needs of clients and a more robust and integrated service system.  It will include the existing workforce as well as the new specialist intervention tenancy service workers.  For further details see page 30.

Refer to Figure 2: System Expansion and Improvement, for a visual representation of how these new initiatives expand and improve on the current system.

Table 1: Homelessness Implementation Plan Initiatives.

| Initiatives | Description | Homeless NP Output |
| --- | --- | --- |
| 1 | Introduction of Same House Different Landlord Program | The Same House Different Landlord Program will enable people experiencing homelessness to move directly into permanent housing transferring the lease to either public housing or a housing association. Tenants will be linked in with support for the duration of their need. This initiative will prevent people experiencing repeat episodes of homelessness through enabling them to remain in the property at the end of the support period once their tenancy is stabilised. This initiative will be supported by the specialist intervention tenancy services in initiative 3. | 16 (b) 16 (d) 17 (d) 17 (g) | Street to home initiatives for chronic homeless people (rough sleepers). Assistance for people leaving institutions. Support for young people aged 12 – 18 years. Assistance for homeless people, including families with children. |
| 2 | Dedicated homelessness facilities | Tasmania will acquire five specific purpose facilities for homeless people over the next two years, two in Hobart, two in Launceston and one in Devonport. One of these facilities in the Hobart CBD will be run along Common Ground like principles. The APTCH election commitment comprising the Commonwealth’s $5 million and the state’s $5 million APTCH and additional matching, will be used in this initiative. | 16 (a) 16 (b) 16 (d) 17 (h) 17 (g) | Implementation of the A Place to Call Home initiative. Street to home initiatives for chronic homeless people (rough sleepers). Assistance for people leaving institutions. Outreach programs to connect rough sleepers to long-term housing and health services Assistance for homeless people, including families with children. |
| 3 | Specialist intervention tenancy services | Specialist intervention tenancy services will provide a multidisciplinary team of specialist tenancy support and professional practitioners who will provide assistance to people: at key transition points where they are at high risk of homelessness including to young people leaving care and protection or youth justice, and adults leaving correctional facilities; with multiple needs who are homelessness or at risk; who experience multiple episodes or extended periods of homelessness (the chronic homeless population); and at risk of tenancy failure in public or private housing. | 16 (a) 16 (b) 16 (c) 16 (d) 17 (d) 17 (g) 17 (h) | Implementation of the A Place to Call Home initiative. Street to home initiatives for chronic homeless people (rough sleepers). Support for private and public tenants to help sustain their tenancies. Assistance for people leaving institutions. Support for young people aged 12 – 18 years. Assistance for homeless people, including families with children. Outreach programs to connect rough sleepers to long-term housing and health services. |
| 4 | Improvements in service coordination and provision | Tasmania will focus on improving service coordination and engagement of mainstream services to ensure a seamless pathway through social housing. This project aims to create an evidence based best practice model through the development of: improved quality and standards; improve performance information; linkages with mainstream services; integration with state health and Human Services reforms; a common assessment framework and practices; and a property register and allocations framework. | 17 (e) | Improvements in service coordination and provision. |
| 5 | State Homelessness Plan | The State Homelessness Plan is being developed by the Social Inclusion Unit within the Tasmanian Department of Premier and Cabinet. The Plan names homelessness as a whole-of-community and whole-of-Government responsibility and aims to improve early identification and referral of people at risk. This initiative will support the implementation of additional and complementary local and regional initiatives. | 17 (i) 17 (l) | National, State, and rural (including remote) homelessness action plans to assist homeless people in areas identified as having high rates of homelessness Workforce development and career progression for workers in homelessness services. |
| 6 | Workforce capacity audit | A workforce capacity audit will be conducted across the sector and a development plan prioritised and implemented over the life of the Agreement. | 17 (l) | Workforce development and career progression for workers in homelessness services. |

Figure 2: System Expansion and Improvement

# Core Output: A Place To Call Home (APTCH)

The intent behind the Commonwealth APTCH election commitment was to ensure that tenants remain in the same house and do not have to move on once their support needs are met. This type of program in Tasmania is to be called Same House Different Landlord. Please note that the Tasmanian Government wrote to Minister Plibersek in 2008 requesting that the APTCH election commitment funds be directed towards a dedicated homelessness facility within the Hobart CDB to be run along Common Ground principles. This request was subsequently supported. This facility whilst utilising APTCH dollars is not described under this output, but rather under Core Output 2, Initiative 2 Dedicated Homelessness Facilities.

Tasmania will implement one major initiative under this core output the Same House Different Landlord Program, it will also directly contribute to the following outputs:

16 (b) Street to home initiatives for chronically homeless people (rough sleepers);

16 (d) Assistance for people leaving child protection services, correctional and health facilities, to access and maintain stable, affordable housing;

17 (d) Support for young people aged 12 – 18 years; and

17 (g) Assistance for homeless people, including families with children.

## Initiative 1: Same House Different Landlord Program

##### New Measure under the Homelessness NP

The Same House Different Landlord Program will enable people experiencing homelessness to move directly into permanent housing through changing lease arrangements to public housing or a housing association tenancy at the end of their support period.  Tenants will be linked in with support for the duration of their need.

The Same House Different Landlord Program will provide property and tenancy management of dwellings allocated for people who are public housing eligible and allocation priority will be given to the target groups identified in the Homelessness NP, especially:

the chronically homeless (rough sleepers);

homeless families with children, young people; and

people leaving child protection services, correctional or health facilities.

The Same House Different Landlord Program will receive referrals from the newly created specialist intervention tenancy services and will match people with appropriate housing that meets their needs.  Properties will be owned by Housing Tasmania initially with the view to transferring stock to the not-for-profit sector in the future where possible.  Allocations will come from a single register.  Tenants will be linked in with tenancy support for the duration of their need.

The initiative will develop guidelines to formalise the Program including: eligibility; access and support provision; how properties will be transferred from public housing stock to replace properties where people have chosen to remain in the property; and how leases will be transferred either to public housing or to a housing association provider.

The management of The Same House Different Landlord Program will be competitively tendered and organisation/s funded under the initiative will be required to allocate and manage tenancies, by agreement between the service funder, the owner, specialist intervention tenancy services or other relevant partners.  All parties will have a mutual commitment to the delivery of improved outcomes for the target groups identified.

This initiative will be implemented in two phases.  In Phase 1 (year 1), 50 new properties will be allocated to this Program funded through the Social Housing NP and additional state effort.  In Phase 2 (year 2) a further 50 new properties will be added; funded through the Stimulus Package and additional state effort bringing a total of 100 new properties into the program.  This equates to an estimated 60 clients in Phase 1 and 120 clients in Phase 2.  The underlying assumptions for client estimates are:

supported accommodation is not time limited however based on current indicators 24 months tenure is anticipated prior to rolling tenancies in to public housing; and

notwithstanding a small number may transfer prior to this time which is indicated by 10 in  the second year of implementation per Phase.

Parallel to the development of the Same House Different Landlord program a review will take place in relation to Housing Tasmania’s existing transitional and Community Tenancy Programs (described below) with the view that by end of Phase 2 more properties from these existing programs may be integrated into the new Same House Different Landlord Program.

# Core Output: Street to home initiatives for chronic homeless people

Tasmania will implement one major initiative to address this output which is the development of four new dedicated homelessness facilities.  This output will contribute to the following outputs:

16 (a) Implementation of A Place to Call Home initiative;

16 (b) Street to home initiatives for chronic homeless people (rough sleepers);

16 (d) Assistance for people leaving child protection services, correctional and health facilities, to access and maintain stable, affordable housing;

17 (h) Outreach programs to connect rough sleepers to long-term housing and health services; and

17 (g) Assistance for homeless people, including families with children.

##### Existing measures

#### Street to home initiatives for chronically homeless people 16 (b)

Mapping of the service systems has identified that there are limited services in this area and no formal program dedicated to providing a street to home service in Tasmania.  Addressing this situation has been identified as a priority.

Supported Residential Facilities (SRF)

The SRF model provides long-term affordable accommodation for low income people with low support needs who do not have the capacity to sustain an independent tenancy and/or desire to live in a communal environment.  Support is provided to residents through onsite support staff.  There are three SRF’s statewide with a fourth planned.

Residents are provided with a room, three meals per day in a communal setting and a weekly linen service in lieu of 85% of income towards rent and board.  The SRF model provides residents with security of tenure under the Residential Tenancy Act 1997 and Residential Tenancy Amendment (Boarding Premises) Act 2003.

There are currently 96 units of accommodation.  Typically each facility will have no more than 35 units of accommodation.  While the service is not gender specific, current residents are predominately single middle aged males.

## Initiative 2: Dedicated homelessness facilities x 5

##### New Measure under the Homelessness NP

In order to help meet the State’s target of halving rough sleepers by the end of 2010, five new dedicated homelessness facilities will be built over the next two years, two in Hobart, two in Launceston and one in Devonport.

The first of these facilities has recently been announced, located at the corner of Liverpool and Barrack St in the Hobart CBD and will be managed by Common Ground Tasmania Inc.  This newly created organisation will develop a Tasmanian version of the Common Ground model.  Its first priorities are to establish stakeholder support for the project at the community level and to secure the involvement of the private and non-government sectors in the services provided to residents and the overall amenity of the facility.

It is undecided at this point if the remaining four facilities will follow the same Common Ground model.  One facility in Launceston will target young people.  This model will be aligned to educational opportunities and provide a mixed model that accommodates young people at risk, with those who are already attending education and training.

Importantly however, all five facilities will provide property and tenancy management and support (where required) to people who are homeless on low incomes, or people with high support needs.

All facilities will seek to establish a sense of community and provide opportunities for personal development and empowerment through strategies such as:

involvement in the design of the model;

resident participation in the establishment and running of governance structures;

peer support and mentoring;

assistance with life skills and developing positive social networks; or

on-site training and employment opportunities.

The facilities will also support a range of visiting services and outreach clinics.  Community Housing Standards will be central to the model in order to support resident participation.

While some support will be provided by the service on-site 24 hours, residents may also be provided with assistance from a range of other services to help them sustain their accommodation and promote their independence.

On 3 September 2008, the Federal Minister for Housing Tanya Plibersek, wrote to the then Minister for Health and Human Services Lara Giddings agreeing in principle to use the $5 million Commonwealth component of capital funding available through APTCH for the construction of a Common Ground like facility in the Hobart CBD.  These funds are being applied to the Liverpool St development.

# Core Output: Support for private and public tenants to help sustain their tenancies.

Tasmania will implement one major initiative under this core output, specialist intervention tenancy services, which will also address all other core outputs and three discretionary outputs:

16 (a), A Place to Call Home;

16 (b), Street to home initiatives for chronically homeless people (rough sleepers);

16 (c), Support for private and public tenants to help sustain their tenancies, including through tenancy support, advocacy, case management, financial counselling and referral services;

16 (d) assistance for people leaving child protection services, correctional and health facilities, to access and maintain stable, affordable housing;

17 (d) Support for young people aged 12 – 18 years;

17 (g) Assistance for homeless people, including families with children;

17 (h) Outreach programs to connect rough sleepers to long-term housing; and health services.

##### Existing measures

#### Support for private and public tenants to help sustain their tenancies 16 (c)

Private Rental

The Private Rental Support Scheme (PRSS) and the Private Rental Tenancy Support Service (PRTSS) are both statewide services for people on low incomes to assist in improving access and sustainability of tenancies within the private rental market. PRSS provides financial assistance while PRTSS provides non-financial tenancy support assistance.

During 2007-08, 4,961 households were assisted under these programs.

During 2008-9 the Australian and State Government will spend $4,091,271 on private rental support programs (not including CRA) in Tasmania; $2,483,234 from the Australian Government under the NAHA and $1,608,037 from State Government. The number of households assisted for the period will be available at the end of the first quarter of the new financial year.

Public Housing

As described above in the Introduction, Aboriginal and public housing has undergone significant service reform.  The two major prongs of the service reform were:

a new organisational structure that emphasised access and support, improved front end and tenancy screening of tenancy at risk indicators and service improvement support to staff; and

the introduction of a new practice paradigm, the Supported Tenancy Practices and Tools (STP&T) requiring staff working with clients with support and complex needs to intervene earlier, coordinate support and work collaboratively to make real differences in clients’ lives.

A major driver for the STP&T was an attempt to minimise clients bouncing between homelessness and public housing.  The premise of the STP&T was that some clients were willing but unable to meet the obligations of their lease without support.  A Triggers and Escalations Pathways was also implemented to provide a framework for reasonable and consistent effort by staff to work with clients engaging in a voluntary capacity.

Engaging support for clients with potential or actual tenancies at risk is now mandated within the STP&T.  This focuses on:

early intervention, at assessment and during a tenancy, to identify potential indicators of at risk tenancies;

‘big picture’ planning to ensure the required strategies and support are in place to give clients the best chance at a sustainable tenancy; and

working more closely with human services to provide the additional supports required.

A review of the first six months of implementation has highlighted a major cultural shift in the public housing workforce and a number of gaps that can not be met by current capacity including allied professional support via psycho-social health assessments, case coordination and management and more sophisticated engagement with mainstream services.

Direct Tenancy Program

The Direct Tenancy Program aims to provide young people with access to accommodation and support to maintain a tenancy.  The tenancy is subject to the young person accepting support from a community organisation.

The Direct Tenancy Program (DTP) is characterised by:

the landlord function being separated from the support function; and

a three-way agreement between Housing Tasmania, the support provider and the tenant.

Housing Tasmania provides operating funding for one youth specific program in southern Tasmania whose key features are:

assessments and allocations conducted by the support provider;

short to medium term tenancies; and

the transfer of the client from the direct tenancy to a mainstream public housing tenancy after the agreed support period and the provision of a replacement property to the support provider (with the exception of a small proportion of stock which is targeted towards student accommodation).

Housing Tasmania allocates 45 public housing properties to the program in southern Tasmania.

The DTP provides assistance to young people specifically but has expanded to include people with mental health issues; people with intellectual and physical disabilities; ex-prisoners; and, people who are chronically homelessness.

These direct tenancies to this expanded group are provided by support organisations funded by alternative support funding sources.   Housing Tasmania allocates approximately 60 properties to this expanded program statewide although it is anticipated that this will grow on the basis of new initiatives described below.

Community Tenancies

The intent of the Community Tenancy Program is to enable organisations to provide supported accommodation for people with specific support needs.  A Community Tenancy is a Tenancy Agreement between the Director of Housing and an organisation.  The provision of support by the organisation is a specific requirement of the Tenancy Agreement, for example:

shelter accommodation for people who are homeless;

residential support facilities for people with intellectual disabilities;

rehabilitation respite for people with mental health issues; and

neighbourhood centres for community support programs.

Housing Tasmania currently allocates over 670 properties to this program.

#### Assistance for people leaving child protection services, correctional and health facilities to access and maintain stable, affordable housing – 16 (d)

Housing Tasmania

In the north-west, a recent pilot program jointly developed by Housing Tasmania and Mental Health Services has assisted eight clients into stable accommodation by providing a more streamlined assessment of registered mental health clients presenting for housing assistance.  Mental Health Services undertake the housing assessment jointly developed with Housing Tasmania and clients are allocated under the Direct Tenancy Program model, as described above, though clients can be older than 25 years.  To be considered eligible for the pilot the client must meet the Housing Tasmania Eligibility Criteria and be:

16 years and older for the first 6 months of the project;

a registered client of Mental Health Services with a commitment to actively case manage the client for the next 6 – 12 months;

homeless or at risk of homelessness or in accommodation which is substandard; and

extremely vulnerable and have a number of complex needs.

Housing Tasmania and Mental Health Services are further refining the model and currently developing procedures for managing the transfer of clients back to mainstream tenancies once clients are identified as being well enough the sustain an independent tenancy.

In the north of the state, Housing Tasmania and Disability, Child, Youth and Family Services have also developed a Young People Leaving Care Transition Program pilot specifically aimed to provide timely and appropriate accommodation to young people exiting child protection services.  A Memorandum of Understanding is currently being drafted between Housing Tasmania and Disability, Child, Youth and Family Services to prioritise young people, from the time they turn 17 years or for young people 16 years and older who are unable to remain in care placements, and where public housing is identified as an appropriate exit point.  These young people can be supported in their tenancy beyond their eighteenth birthday regardless of their age at entry.

In the south-west, Housing Tasmania redeveloped 11 properties specifically for people receiving support from Richmond Fellowship, an organisation that provides services to people with mental health conditions.  The properties had substantially improved internal and external amenity to suit the needs of this client group.  These properties are made available using the Community Tenancy model.

In the south-east, Housing Tasmania provides 12 units of accommodation for people who have exited long-term mental health institutional care.  Support is also provided for this client group by Richmond Fellowship and operates on a Community Tenancy model.  In both cases, the accommodation and support provided foster more independent living opportunities for clients.

Direct Tenancies Program

See above for details.

Community Tenancies Program

See above for details.

Specialist Homelessness Services:

Bethlehem House Parolee Transitional Accommodation Project

The Parolee Transitional Accommodation Project (PTAP) is funded by the DHHS through the Housing Innovations Unit.  Housing Tasmania has made four properties available to PTAP through a Community Tenancy arrangement.

The project commenced on 1 November 2008 and provides assistance to unaccompanied males in the southern region of the State.  Assistance is provided within a case management framework and is based on a comprehensive risk and need assessment.

In the first 3 months of operation the project received 13 referrals and accepted 10 of the individuals referred into the program.

Transitional Support Model for ex-Prisoners Pilot Program

The Transitional Support Model for Ex-Prisoners (TSMP) is a SAAP V Innovation and Investment funded project which is delivered by The Salvation Army.  The Pilot program operates within a case management framework and aims to reduce the rate of homelessness of males and females exiting prison by providing housing and outreach assistance that assist them to obtain long term stable housing.  TSMP aims to maximising independence, self reliance and integration into the community and therefore reduce re-offending.

The program commenced in southern Tasmania in January 2008 and in north/northwest of Tasmania in March 2008.  In the first 9 month of operation, the southern service housed 53 clients.  The north/northwest service received 20 referrals and housed 10 clients in the first 7 months of operation.

Funding for the TSMP was for a 2 year pilot and will cease on 30 June 2009.  The program will continue to run through until the end of the 2009 calendar year due to the delayed commencement.

#### Support and assistance for young people aged 12 to 18 years - 17 (d)

Human Services: Out of Home Care

Out of home care services provide placements for children and young people who are unable to live with their parents because of care and protection concerns requiring the state’s intervention.  In Tasmania the majority of these placements are provided through foster care and group home/cottage care.

A part of the Human Services reforms is the introduction of regional Gateway Services at a local level to be provided by the non-government sector along with an enhanced family support service and Child Protection systems.  Another component of this reform is the restructuring of the Out of Home Care system which is an important safety net to protect young people 12-18 years from becoming homeless. Under the Out of Home Care reform increased resources will be directed at Foster Care and Kinship Care and away from the current emphasis on residential care.

Specialist Homelessness Services

The Tasmanian Government provides short to long term supported residential accommodation (Mara House, YASTas) or individual community based placements (PASS) specifically targeted at young people from 13 to 18 years of age.

This includes young people who are homeless, unable to live at home or with extended families, exiting juvenile institutions or are under statutory care and protection arrangements.

Number of young people can be accommodated at any one time:

| Mara | 6 |
| --- | --- |
| YASTas | 6 |
| PASS | 49 |

Number of young people assisted 2007-08*

| Mara | 2007-08: 46 clients on 62 occasions |
| --- | --- |
| YASTas | 2007-08: 29 clients on 40 occasions |
| PASS (statewide) | 2007-08: 35 clients on 56 occasions |

* Completed support periods and ongoing support periods

Youth Beat

Youth Beat is a program operated by Mission Australia in the Glenorchy municipality located in Southern Tasmania.  The program is funded through the Tasmanian Community Fund and the National Illicit Drugs Strategy. Mission Australia is currently seeking ongoing funding for the program.

Youth Beat is aimed at re-engaging homeless young people aged 12 to 24 years with health and housing services, family, education, community and recreation activities.  The program is a mobile outreach service which provides counselling, information and support out of business hours, and follow-up referral during business hours.  The program also has a presence at most community events, major sporting days, education days and drug and alcohol workshops.

The DHHS does not have access to definitive data regarding the number of young people assisted through the program.

Staying Put

Single young people who are unemployed or in receipt of low incomes experience major difficulties finding affordable housing, particularly in the case of young people who for a range of reasons do not have support from their parents to help them make the transition to independent housing.

Staying Put focuses on supporting clients to maintain tenancies in mainstream public and private rental housing, as well supporting young people in a small number of Direct and Community Tenancies.

The primary aim of this program is to improve housing outcomes for young people by assisting them to develop the skills they need in order to successfully maintain a tenancy.

The benchmark for client interventions is eight weeks intensive outreach support and a caseload of sixteen clients.

79 young people were assisted in 2007/08.

#### Assistance for homeless people, including families with children to stabilise their situation and to achieve sustainable housing - 17 (g)

Specialist Homelessness Services

A range of accommodation services aimed at families are funded in the state.  This includes brokerage, immediate emergency accommodation, private rental support, private rental tenancy support, case planning and support, transitional support services as well as specific transitional support model for children within immediate emergency accommodation facilities.

Number of families that can be accommodated at any one time:

| Oakleigh House | NW | 3 |
| --- | --- | --- |
| CHILD | Tas | 30 |

Number of families assisted 2007-08:

| Oakleigh House | NW | 2006/07: 89 clients on 139 occasions* |
| --- | --- | --- |
| CHILD# (Pilot I&I project) | Tas | 39 which includes 62 children (over a 12 month period of data) |

*  Range in client numbers due to some clients not providing consent. 85 clients gave consent, but 6 where clients did not give consent.

# CHILD (Children who are Homeless Intervention, Learning and Development) is a pilot SAAP V Innovation and Investment project.

## Initiative 3: Specialist intervention tenancy services

##### New Measures under the Homelessness NP

The new specialist intervention tenancy services will be directed at complementing existing tenancy support programs available in the non-government sector but at the high end.  This is in recognition that there is currently no specialist service to respond to this target group, particularly those who are public or private renters and at risk of homelessness due to their high needs.

Under the specialist intervention tenancy service, Tasmania will provide additional and improved assistance to people:

at key transition points where they are at high risk of homelessness including to young people leaving care and protection or youth justice, and adults leaving correctional and health facilities;

with multiple needs who are homelessness or at risk of homelessness;

who experience multiple episodes or extended periods of homelessness (the chronic homeless populations); and

at risk of tenancy failure in private or public housing.

A key function of the new specialist services will be the capacity to develop and maintain links and effective working relationships with mainstream, specialist homeless and housing services which facilitate access and influence service outcomes for people at risk.

The specialist intervention tenancy services will be staffed by multi-disciplinary teams.  Teams will be guided by formal structures and agreements that have: clear objectives, linkages, defined areas of leadership and responsibility, assessment and referral processes, shared outcomes, systematic policy and program evaluation using an action research approach and adequate funding.  The multi-disciplinary teams will also include advanced practitioners and allied health professionals who are highly skilled, competent and equipped to work with people with a multiplicity of need.  Advanced practitioners will have specialist skills and expertise in areas such as mental health, drug and alcohol, and counselling.  Each area team will consist of at least one staff member with a dedicated child and youth focus and an advanced practitioner focussed on sustaining high risk tenancies in public and Aboriginal housing.  They will have access to the Same House Different Landlord 50 new properties in Phase 1 and 100 properties in Phase 2.

Advanced practitioners will respond to the individual needs of clients through active outreach, psycho-social assessment of need, case coordination and management, ongoing tenancy support, advocacy, and appropriate referral and specialist treatment liaison as required.

Furthermore, the implementation of Phase 2 will expand the capacity of the initiative by not only implementing the program statewide but also providing an additional advanced practitioner into each area that will have a primary focus on sustaining public housing tenancies and supporting their transition to private or other social housing opportunities where appropriate for the client.

## The specialist intervention tenancy services will increase workforce capacity through the establishment of advanced practitioners which includes allied health professional positions which are key gaps in the current service system.

## Discretionary Output: Improvement in service coordination and provision.

Tasmania will implement a series of improvement initiatives to address the following discretionary output:

17 (e) Improvement in service coordination and provision.

As described in the introduction, coordination and service integration at a local level is a major priority of the Tasmanian Government. DHHS as already outlined, have major new initiatives around Primary Health and Acute Care, Mental Health, Drug and Alcohol, and Human Services reforms in Family Support Services, Out of Home Care, Child Protection and Disability Services.

##### Existing Measures

#### Improvement in service coordination and provision - 17 (e)

A key policy initiative within the DHHS is the Agency Collaboration Strategy (ACS) which provides a formal framework for improving the Agency’s response to people with complex and exceptional needs including those in public housing.  The ACS aims to improve the management and provision of services for Agency clients requiring a complex mix of supports and services not easily achieved at an operational level.  This is targeted at key coordination points within the Agency that have the resources and authority to circuit break service blockages.

Housing Tasmania is responsible for working in collaboration with other Agency business units to meet the needs of these clients.

A specific strategy introduced in Housing Tasmania’s broader service delivery reform outlined above is a Service Coordination Panel.  This sits within the broader ACS framework but provides a formal service coordination response at the direct service delivery level.  The strategy has provided the necessary infrastructure to staff to consistently convene and coordinate the needs of clients with complex and/or support needs so as to sustain their tenancies.

Specialist Homelessness Services

Current specialist homelessness services are managed through service agreements and quality assurance mechanisms where by following a quality assurance assessment each service is to develop a service improvement plan.

All thirty-four specialist homelessness services (formerly SAAP funded services) have been reviewed against the Quality Improvement Council (QIC) Core Module and the SAAP Service Delivery Standards.  As at the end of the July – December 2008 reporting period twenty-one services had achieved a ‘met’ or ‘met in part’ rating against all standards and eleven services had one or more ‘not met’ ratings.  Of the reviewed services, eight had submitted a Quality Work Plan (QWP).  Three SAAP funded services were still awaiting their audited report at the end of the reporting period.

Service coordination is achieved through regular regional forums which bring together all specialist homelessness services in that particular area to discuss key issues, opportunities, service gaps and responses.

## Initiative 4: Improvements in Service Coordination and Provision

##### New Measures under the Homelessness NP

Achieving outcomes for all core and discretionary outputs under the Homelessness NP will be underpinned by the Improvements in Service Coordination and Provision initiative 17 (e).

The improvements in service coordination and provision initiative involves a suite of activities aimed at improving and integrating the entire homelessness and support service system and therefore will contribute to successful outcomes in the three previous initiatives. Under this initiative Tasmania will focus on improving service coordination and engagement of mainstream services to ensure a seamless pathway through social housing.  This project aims to create evidence based best practice models through the development of:

improved quality and standards;

improved performance information;

linkages with mainstream services;

a common assessment framework and practices;

a property register and allocations framework; and

information management infrastructure.

This work will be informed by an analysis of existing eligibility, assessment and allocation policies and practices and will include refinement of current access and support programs.  The project will build on the achievements of the current Integrated Continuum of Support model and establish an evidence base for further service development.

To support the practical implementation of better service coordination and improvements, business processes and systems will be developed or improved including:

capacity to share appropriate levels of client information and make active referrals;

ability to monitor availability of properties in real time (a property/bed register);

appropriate matching of clients with accommodation and support where required;

formal mechanism to build in the capacity to measure success including tracking individual and service outcomes;

linking skills development through training; and

reporting.

# Discretionary Output: National, State and rural (including remote) homelessness action plans.

Tasmania will develop a State Homelessness Plan to address these discretionary outputs:

17 (i) National, State and rural (including remote) homelessness action plans to assist homeless people in areas indentified as having high rates of homelessness; and

17 (l) Workforce development and career progression for workers in homelessness services.

##### Existing Measures

#### National, State and rural (including remote) homelessness action plans to assist homeless people in areas indentified as having high rates of homelessness – 17 (i)

The Tasmanian Government has announced that a State Homelessness Plan is to be developed by the Social Inclusion Unit within the Department of Premier and Cabinet under a social inclusion framework.

#### Workforce development and career progression for workers in homelessness services – 17 (l)

The State Homelessness Plan to be developed by the Social Inclusion Unit within the Department of Premier and Cabinet will include measures to develop awareness of homelessness within the broader community as well as within mainstream services such as schools and General Practitioners.  The Plan will also have a focus area targeting the prevention and early identification of people at risk of homelessness, as well as the development of a range of skills in the mainstream service system and more specialist skills in the homelessness service system.

## Initiative 5: State Homelessness Plan

##### New Measures under the Homelessness NP

As already explained in this document a State Homelessness Plan is being developed by the Social Inclusion Unit in collaboration with Housing Tasmania to ensure alignment with the Homelessness Implementation Plan. A key tenet of the State Homelessness Plan is that homelessness is a whole-of-government and whole-of-community responsibility.

The Plan will incorporate the effort under the National Affordable Housing Agreement (NAHA) and associated National Partnership Agreements (NPs) on Homelessness, Social Housing and Indigenous Housing, and the Nation Building and Jobs NPA.

The State Homelessness Plan will also specify initiatives against specific state priorities, such as halving the benchmark number of 385 rough sleepers to 193 by 2010 and other local and regional initiatives. Addressing homelessness will be a priority for all mainstream government services.  Prevention of homelessness and the appropriate delivery of services to people experiencing or at risk of homelessness will be a priority.  All parts of the state including rural and remote areas will be included in the Plan’s initiatives.

Funds identified in this initiative will contribute to the implementation of actions identified as priorities within the Plan at a local level.  The State is taking responsibility for the consultation process, administration, co-ordination of activities, monitoring and reporting as well as the funding of specific initiatives.  Funds under Initiative 5 will contribute towards planning, realigning services and change management activities at a local and regional level.  This effort will be targeted at what changes are required to ensure specialist homelessness services and mainstream services are better co-ordinated and where possible more closely engaged in the early identification and prevention of people at risk of homelessness.

## Discretionary Output: Workforce development and career progression for workers in homelessness services.

Tasmania will implement a series of initiatives to address this discretionary output:

17 (l) Workforce development and career progression for workers in homelessness services.

##### Existing Measures

#### Workforce development and career progression for workers in homelessness services – 17 (l)

The Community Services Industry Plan 2009-2012 developed in 2008 is driven and owned by community services organisations across Tasmania.

The Plan has been developed to enable community organisations to define the priority issues that the industry, government and other stakeholders must address to ensure quality services in Tasmania continue to be delivered on behalf of the community.

The Plan identifies four key areas that must drive reform, investment and improvement in practice within the industry:

building on our strengths;

securing a workforce for the future;

getting the right sort of investment in social services; and

strengthening the social service system.

## Initiative 6: Workforce capacity audit and development plan

##### New Measures under the Homelessness NP

A workforce capacity audit will be conducted on the current specialist homelessness service sector as well as the skills and capabilities requirements of the new initiatives outlined in this Plan, for example the specialist intervention tenancy services.  While many workers in the current specialist homelessness service sector are highly skilled, there are concerns that the workforce generally still requires some up skilling.  This is particularly the case given the increasing numbers of highly complex clients presenting to specialist homelessness services and the significant system changes within the health and human services sector within Tasmania in recent years.  Systematic measures and resources need to be put in place to ensure the availability of quality training to ensure that service provision is of a high standard and is flexible enough to respond to a high turnover of staff in this sector.

Currently specialist homelessness sector training is provided in a limited way through an external generic training provider.  A greater level of specification is necessary to identify the learning and development requirements to better meet the needs of the sector.  The audit is expected to provide this level of information.

The non-government sector through TasCOSS has conducted a high level industry plan for the third sector during 2007-2008.  This audit will complement and provide more specific information on the needs of the specialist homelessness sector and information on the current capacity of the system and its workforce to move to new models of service provision and provide more uniform and higher quality services.

Noting the significant changes to the sector in years 1 and 2, the Audit will be conducted in 2011-12 and workforce development plan prepared.  The Plan will be implemented in subsequent years.

# Remaining Discretionary Outputs:

In order to focus effort on priority services and population target groups Tasmania will not address the following discretionary outputs in the initial years:

17 (a) Support services and accommodation to assist older people who are homeless or at risk;

17 (b) Services to assist homeless people with substance abuse to maintain stable accommodation;

17 (c) Services to assist homeless people with mental health issues to secure or maintain stable accommodation;

17 (f) Support for women and children experiencing domestic and family violence to stay in their housing;

17 (j) Support for children who are homeless or at risk, including to maintain contact with the education system; and

17 (k) Legal services for people who are homeless.

(These target groups will be picked up by the specialist intervention tenancy services, one would hope. We would need to review how well these needs are addressed by tenure neutral tenancy support to inform possible development of targeted services.)

There may be scope in the out years to address some of these discretionary outputs.

NATIONAL PARTNERSHIP AGREEMENT ON HOMELESSNESS – FUNDING

| YEAR | 1 (2008/09) $m | 2 (2009/10) $m | 3 (2010/11) $m | 4 (2011-12) $m | 5 (2012/13) $m | TOTAL $m |
| --- | --- | --- | --- | --- | --- | --- |
| Commonwealth contribution |  |  |  |  |  |  |
| capital | 0.4 | 2.6 | 2.0 | 0.0 | 0.0 | 5.0 |
| recurrent | 0.0 | 1.7 | 2.4 | 2.6 | 2.6 | 9.3 |
| Tasmania contribution |  |  |  |  |  |  |
| capital | 0.0 | 7 | 2.5 | 0.0 | 0.0 | 9.5 |
| recurrent | 0.0 | 0.0 | 3.7 | 2.7 | 2.7 | 9.1 |
| TOTAL FUNDING | 0.4 | 11.3 | 10.6 | 5.3 | 5.3 | 32.9 |

# Text boxes

Assessment

Support

Information

Referral

Brokerage Funds

Immediate

Emergency

Accommodation

Transitional

Support

Private

Rental

Supported

Residential

Facilities

Public & Aboriginal

Housing

Private Rental Tenancy Support

Private Rental 
Support Scheme

Staying Put (Youth)

Home

Ownership

Shelters

Dispersed

Model

Transitional

Accommodation

Direct

Tenancies

}

Integrated Continuum of Support (ICOS)

Community

Tenancies