Schedule

FEE-FREE TAFE SKILLS AGREEMENT

FEDERATION FUNDING AGREEMENT – EDUCATION AND SKILLS

|  |  |
| --- | --- |
| **Part 1: Formalities and operation of schedule** | |
| Parties | Commonwealth  New South Wales  Victoria  Queensland  Western Australia  South Australia  Tasmania  Australian Capital Territory  Northern Territory |
| Duration | This Schedule is expected to expire 30 June 2027, or on completion of the activities in this Schedule, including final performance reporting and processing of final payments against milestones. |
| Purpose | This Schedule establishes shared funding arrangements between the Commonwealth and states and territories (the States) to deliver Fee-Free TAFE Tranche 1 and 2 places in agreed areas of priority set out in Appendices A and F, enhanced infrastructure set out in Appendix B and C, and the Fee-Free Construction and pre-apprenticeship places at Appendix G.    Through Fee-Free TAFE, support will be available for priority groups including First Nations Australians, young people (17-24), people out of work or receiving income support, unpaid carers, women facing economic insecurity, women undertaking study in non-traditional fields, people with disability and certain categories of visa holders.    This agreement will put TAFE at the centre of VET, while recognising varied State delivery contexts.  This agreement recognises the commitment of all jurisdictions to address housing supply and to increase the pipeline of skilled workers to the construction industry as part of the Fee-Free Construction and pre-apprenticeship places. |
| Estimated financial contributions | The Commonwealth will provide an estimated total financial contribution to the States for Fee-Free TAFE Tranche 1 of $493 million in respect of Appendix A and $50 million for the TAFE Technology Fund as described in Appendix B. The Commonwealth will also provide $6.85 million for VET Data Infrastructure Reforms as described in Appendix C. The Commonwealth will provide an estimated total financial contribution to the States for Fee-Free TAFE Tranche 2 (FFTT2) of $414.11 million in respect of Appendix F and Table 1a. The Commonwealth will provide an estimated total financial contribution to the States for Fee-Free Construction of $86.4 million in respect of Appendix G and Tables 1b and 2a.  States will match the Commonwealth’s contribution for Fee-Free TAFE Tranche 1 (Tables 1, 2 & 3 refer).  State-matched funding will be additional to the Baseline Funding commitment in 2023 described in Appendix A Table 1. States further commit to an increase in levels of expenditure on public providers. |
|  | Table 1: Estimated financial contributions for Fee-Free TAFE Tranche 1 places (Appendix A refers)  **($ million)** 2022-23 2023-24 Total   |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **Estimated total budget**  **Less estimated National Partnership payments** |  |  | 597.76 | 256.22 | 853.98 | |  |  | 298.88 | 128.11 | 426.99 | | New South Wales  Victoria |  |  | 94.02  77.46 | 40.30  33.20 | 134.32  110.66 | | Queensland |  |  | 61.29 | 26.27 | 87.56 | | Western Australia |  |  | 31.37 | 13.44 | 44.81 | | South Australia |  |  | 20.57 | 8.82 | 29.39 | | Tasmania |  |  | 6.29 | 2.70 | 8.99 | | Australian Capital Territory |  |  | 5.01 | 2.15 | 7.16 | | Northern Territory  Non-Commonwealth contributions |  |  | 2.87  298.88 | 1.23  128.11 | 4.10  426.99 |   The Commonwealth will provide an estimated total financial contribution to the States for Fee-Free TAFE Tranche 2 (FFTT2) of $414.11 million in respect of Appendix F and Table 1a in accordance with the funding principles of the Agreement as described in Table 1a.  Table 1a: Funding for FFTT2 by jurisdiction (Appendix F refers):  **($ million)** 2023-24 2024-25 2025-26 2026-27 Total   |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **Estimated total budget**  New South Wales | 165.642 | 0 | 124.231 | 124.231 | 414.104 | | 51.733 | 0 | 38.612 | 38.519 | 128.864 | | Victoria | 42.555 | 0 | 32.148 | 32.260 | 106.963 | | Queensland | 33.975 | 0 | 25.494 | 25.501 | 84.970 | | Western Australia | 17.786 | 0 | 13.356 | 13.363 | 44.505 | | South Australia | 11.493 | 0 | 8.536 | 8.498 | 28.527 | | Tasmania | 3.593 | 0 | 2.681 | 2.675 | 8.949 | | Australian Capital Territory | 2.921 | 0 | 2.214 | 2.225 | 7.360 | | Northern Territory | 1.586 | 0 | 1.190 | 1.190 | 3.966 |   Source: Calculation based on state population projections of 2023-24 Commonwealth Budget.    Payments are to be made in accordance with Part 2: Performance Milestones and Payment Summary for FFTT2.  The Commonwealth will provide an estimated total financial contribution to the States for Fee-Free Construction of $86.4 million in respect of Table 1b and Appendix G for delivery across the 2025 and 2026 calendar years.  Table 1b: Funding for 20,000 Fee-Free places in construction, including up to 5,000 pre-apprenticeships (Appendix G refers)   |  |  |  |  | | --- | --- | --- | --- | | **($ million)** | **2024-25** | **2025-26** | **Total** | | **Estimated Total Budget** | **39.404** | **39.404** | **78.808** | | New South Wales | 12.312 | 12.305 | 24.616 | | Victoria | 10.126 | 10.161 | 20.287 | | Queensland | 8.093 | 8.098 | 16.191 | | Western Australia | 4.282 | 4.277 | 8.559 | | South Australia | 2.710 | 2.692 | 5.402 | | Tasmania | 0.828 | 0.820 | 1.647 | | Australian Capital Territory | 0.688 | 0.689 | 1.376 | | Northern Territory | 0.366 | 0.363 | 0.729 |   Source: Calculation based on state population projections from the 2024-25 Commonwealth Budget. Discrepancies in tables between totals and sums of components are due to rounding.  Payments are to be made in accordance with Part 2: Performance Milestones and Payment Summary for Fee-Free Construction.  Table 2: Estimated financial contributions for ancillary funding for Fee-Free TAFE Tranche 1 (Appendix A refers)   |  |  |  |  | | --- | --- | --- | --- | | **($ million)** | 2022-23 | 2023-24 | Total | | **Estimated total budget**  **Less estimated National Partnership payments** | 59.80 | 25.60 | 85.40 | | 29.90 | 12.80 | 42.70 | | New South Wales | 9.40 | 4.03 | 13.43 | | Victoria | 7.75 | 3.32 | 11.07 | | Queensland | 6.13 | 2.63 | 8.76 | | Western Australia | 3.14 | 1.34 | 4.48 | | South Australia | 2.06 | 0.88 | 2.94 | | Tasmania | 0.63 | 0.27 | 0.90 | | Australian Capital Territory | 0.50 | 0.21 | 0.72 | | Northern Territory | 0.29 | 0.12 | 0.41 |   Non-Commonwealth contributions 29.90 12.80 42.70    Table 2a: Estimated financial contributions for student support and ancillary funding for Fee-Free Construction places, including up to 5,000 pre-apprenticeships (Appendix G refers).   |  |  |  |  | | --- | --- | --- | --- | | **($ million)** | **2024-25** | **2025-26** | **Total** | | **Estimated Total Budget** | **5.118** | **2.429** | **7.547** | | New South Wales | 1.599 | 0.759 | 2.358 | | Victoria | 1.315 | 0.626 | 1.942 | | Queensland | 1.051 | 0.499 | 1.550 | | Western Australia | 0.556 | 0.264 | 0.820 | | South Australia | 0.352 | 0.166 | 0.518 | | Tasmania | 0.107 | 0.051 | 0.158 | | Australian Capital Territory | 0.089 | 0.042 | 0.132 | | Northern Territory | 0.048 | 0.022 | 0.070 |   Source: Calculation based on state population projections from the 2024-25 Commonwealth Budget. Discrepancies in tables between totals and sums of components are due to rounding.  Table 3: Estimated financial contributions for additional student support for Fee-Free TAFE Tranche 1 (Appendix A refers)   |  |  |  |  | | --- | --- | --- | --- | | **($ million)** | 2022-23 | 2023-24 | Total | | **Estimated total budget** | 47.26 | 0.00 | 47.26 | | **Less estimated National Partnership payments** | 23.63 | 0.00 | 23.63 | | New South Wales | 7.44 | 0.00 | 7.44 | | Victoria | 6.11 | 0.00 | 6.11 | | Queensland | 4.84 | 0.00 | 4.84 | | Western Australia | 2.48 | 0.00 | 2.48 | | South Australia | 1.63 | 0.00 | 1.63 | | Tasmania | 0.50 | 0.00 | 0.50 | | Australian Capital Territory | 0.40 | 0.00 | 0.40 | | Northern Territory | 0.23 | 0.00 | 0.23 | | Non-Commonwealth contributions | 23.63 | 0.00 | 23.63 |   Table 4: VET Data Infrastructure Reforms   |  |  |  |  |  | | --- | --- | --- | --- | --- | | **($ million)** | 2022-23 | | 2023-24 | Total | | **Estimated total budget** | | 3.89 | 2.94 | 6.83 | | New South Wales | 0.75 | | 0.57 | 1.32 | | Victoria | 0.53 | | 0.40 | 0.93 | | Queensland | 0.53 | | 0.40 | 0.93 | | Western Australia | 0.53 | | 0.40 | 0.93 | | South Australia | 0.53 | | 0.40 | 0.93 | | Tasmania | 0.36 | | 0.27 | 0.63 | | Australian Capital Territory | 0.33 | | 0.25 | 0.58 | | Northern Territory | 0.33 | | 0.25 | 0.58 |   Table 5: Estimated financial Contributions TAFE Technology Fund   |  |  |  |  | | --- | --- | --- | --- | | **($ million)** | 2023-24 | 2024-25 | Total | | **Estimated total budget** | 19.768 | 30.232 | 50.000 | | New South Wales | 5.250 | 5.450 | 10.700 | | Victoria | 2.940 | 5.670 | 8.610 | | Queensland | 4.060 | 4.740 | 8.800 | | Western Australia | 5.768 | 3.572 | 9.340 | | South Australia | 0.000 | 4.252 | 4.252 | | Tasmania | 1.750 | 0.750 | 2.500 | | Australian Capital Territory | 0.000 | 3.200 | 3.200 | | Northern Territory | 0.000 | 2.500 | 2.500 |   \*May not total $50 million due to unallocated funds. |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Additional terms | The Parties agree to implement this Schedule in accordance with the funding principles set out under the Appendices of this Schedule, and bilateral Implementation Plans.  Implementation Plans for Fee-Free TAFE will be agreed by the Commonwealth and each state individually, with finalisation triggering Milestone Payment 1 for that state.  To support FFTT2, new Implementation Plans must be submitted by all States by 29 September 2023 or as negotiated between senior officials.  FFTT2 places for each jurisdiction are set out in Table 6.  Table 6: FFTT2 Places by jurisdiction   |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **($ million)** | 2023-24 | 2024-25 | 2025-26 | 2026-27 | Total | | **Estimated total places** | 50,300 | 100,300 | 100,300 | 50,300 | 301,200 | | New South Wales | 24,600 | 49,100 | 49,100 | 24,600 | 147,400 | | Victoria | 10,500 | 20,900 | 20,900 | 10,500 | 62,800 | | Queensland | 7,200 | 14,500 | 14,500 | 7,200 | 43,400 | | Western Australia | 3,700 | 7,400 | 7,400 | 3,700 | 22,200 | | South Australia | 2,500 | 5,000 | 5,000 | 2,500 | 15,000 | | Tasmania | 800 | 1,500 | 1,500 | 800 | 4,600 | | Australian Capital Territory | 600 | 1,200 | 1,200 | 600 | 3,600 | | Northern Territory | 400 | 700 | 700 | 400 | 2,200 |   Governments are committed to delivering 480,000 Fee-Free TAFE places.  To support Fee-Free Construction, new Implementation Plans must be submitted by all States by 18 October 2024 or as negotiated between senior officials. Fee-Free Construction places for each jurisdiction are set out in Tables 7 and 7a.  Table 7: Fee-Free Construction Places by Jurisdiction, to be allocated across 2025 and 2026 calendar years.  **Estimated total places**  15,000  New South Wales 4,700  Victoria 3,900  Queensland 3,100  West Australia 1,600  South Australia 1,000  Tasmania 310  Australian Capital Territory 260  Northern Territory 130  Table 7a: Fee-Free Pre-apprenticeship places by Jurisdiction  **Estimated total places**   **5,000**  New South Wales 1,600  Victoria 1,300  Queensland 1,000  West Australia 540  South Australia 340  Tasmania 100  Australian Capital Territory 80  Northern Territory 40  Through Implementation Plans, officials will agree implementation arrangements so that Fee-Free TAFE places are available across each year of the Agreement to avoid service gaps.  Implementation plans can be varied by agreement between the relevant senior Commonwealth and state officials to assist States to manage demand for places, including by counting over-enrolments in areas of national priority towards places for the following year.  Changes to the appendices of this Schedule may be agreed in writing between the state and Commonwealth Skills Ministers, either multilaterally or bilaterally where the changes will not affect other States.  Given the importance of addressing key skills shortages in the economy, regular reporting is considered necessary.  The parties also agree to share the costs of the debt-not-expected-to-be-repaid for Government Subsidised students under the VET Student Loans Program set out in Appendix D. |

|  |  |  |
| --- | --- | --- |
| **Part 2: Performance milestones and payment summary** |  |  |
| **Performance Milestones and Payments for the Fee-Free TAFE Fund (Tranche 1)**  ***Provision of additional Fee-Free training places in areas of identified skills need in accordance with principles outlined at Appendix A*.** | **Due** | **Payment** |
| **Performance Milestone 1**  States agree and sign up to the Schedule.  Commonwealth and States agree to the FFT Fund Implementation Plan. In doing this:   * The State has provided an Implementation Plan that outlines how they will operationalise Fee-Free TAFE   in their jurisdiction, consistent with the principles and areas requiring Commonwealth agreement in Appendix A and including any specific bilateral parameters and local fraud and integrity measures.   * Commonwealth senior officials to review and either confirm agreement or provide feedback within two weeks of receiving an Implementation Plan from the State. * If updates are required, the State to provide revised Implementation Plan within 2 weeks. | Within 30 days of signing the schedule or 1 January 2023 or following Commonwealth and State agreement to the State’s FFT Fund Implementation Plan, whichever is later. | The total of:   * 40% of the State’s allocation of funding for Fee-Free TAFE places; * 100% of the State’s allocation of funding for Student Support Services; and * 40% of the State’s allocation of Ancillary funding. |
| **Performance Milestone 2**  The State has provided quarterly reporting consistent with Part 3 of this Schedule which shows that enrolments in eligible training places have committed a minimum of 40 per  cent of the total of the Fee-Free Places and Ancillary Purposes funds for expenditure.  State funding for ancillary purposes will count toward meeting this milestone on a pro-rata basis. For example: To meet the 40 per cent committed funding utilisation milestone, a minimum of 36 per cent utilisation must be met through enrolments, with a maximum of 4 per cent met through ancillary funding. | May 2023  (Estimated) | The total of:   * 30% of the State’s allocation of Fee-Free TAFE places; and * 30% of the State’s allocation of funding for Ancillary Purposes. |
| **Performance Milestone 3**  The State has provided quarterly reporting consistent with Part 3 of this Schedule which shows that enrolments in eligible training places have committed a minimum of 70 per cent of the Fee-Free TAFE Places and Ancillary Purposes funds for expenditure.  State funding for ancillary purposes will count toward meeting this milestone on a pro-rata basis. For example: To meet the 70 per cent committed funding utilisation milestone, a minimum of 64 per cent utilisation must be met through enrolments, with a maximum of 6 per cent met through ancillary funding. | November 2023  (Estimated) | The total of:   * 30% of the State’s allocation of the Fee Free TAFE places: and * 30% of the State’s allocation of funding for Ancillary Purposes. |

|  |  |  |  |
| --- | --- | --- | --- |
| **Performance Milestones and Payments for the Fee-Free**  **TAFE Fund (FFT Fund) Fee-Free TAFE Tranche 2** | **Due** |  | **Payment** |
| **Performance Milestone 1**  States agree and sign up to the Deed of Variation.    Commonwealth and States senior officials agree to the FFTT2 Implementation Plan. | Within 30 days of signing this Deed of  Variation or 1 January 2024, whichever is later |  | • A first payment of 40% of the State’s FFTT2 funding. |
| **Performance Milestone 2**  The State has provided quarterly reporting consistent with Part 3 of this Schedule which shows that the value of enrolments in eligible training places in the jurisdiction has reached a minimum of 40 per cent of the FFTT2 expenditure. | Estimated for July 2025 |  | • A second payment of 30% of the State’s  FFTT2 funding, based on achievement of 40% of the total expenditure of FFTT2 funds. |
| **Performance Milestone 3**  The State has provided quarterly reporting consistent with Part 3 of this Schedule which shows that the value of enrolments in eligible training places in the jurisdiction has reached a minimum of 70 per cent of the FFTT2 expenditure. | Estimated for December 2026 |  | • A final payment of 30% of the State’s  FFTT2 funding, based on achievement of 70% of the total expenditure of FFTT2 funds. |

|  |  |  |
| --- | --- | --- |
| **Milestones and Payments – TAFE Technology Fund Committed Projects (Appendix B)**  ***\*Performance Milestones for projects agreed from the TAFE Technology Funding Pool will be considered in the application assessment process.*** | **Due** | **Payment** |
| **Performance Milestone 1**  States and Commonwealth agreement to (individual) TAFE Technology Fund Project Plan(s).    State and territory and Commonwealth senior officials will agree to (individual) TAFE Technology Fund Project Plan(s). | From 31 March  2023 | 70% allocation for TAFE Technology Fund project. |
| **Performance Milestone 2**  Finalisation of project, as demonstrated by agreement completion criteria and final project acquittal report to the Commonwealth.    Finalisation of project, as demonstrated by completion criteria outlined in the project plan agreed by Commonwealth and state and territory senior officials and final project acquittal report to the  Commonwealth. | As outlined in the (individual) Project Plan. | 30% allocation for TAFE Technology Fund project. |
| **Milestones and Payments - Strengthening VET Data**  **(Appendix C)** | **Due** | **Payment** |
| **Performance Milestone 1**  Signing of this Schedule and a commitment to collaborate on the  VDS program | 1 January 2023 | 57% State allocation of the funding for VET data Infrastructure. |
| **Performance Milestone 2**  Development of State impact assessments and high-level roadmaps | 1 July 2023 | 43% State allocation of the funding for VET data Infrastructure. |

|  |  |  |  |
| --- | --- | --- | --- |
| **Performance Milestones and Payments for  Fee-Free Construction** | **Due** |  | **Payment** |
| **Performance Milestone 1**  States agree and sign up to the updated Schedule.    Commonwealth and States agree to the FFT Construction Implementation Plan. | Within 30 days of signing this Schedule or  1 January 2025 or following Commonwealth and State agreement to the State’s Implementation Plan, whichever is later. |  | * 50 per cent of funding for places on sign-up * 100 per cent of student support funding * 50 per cent of ancillary funding |
| **Performance Milestone 2**  The State has provided quarterly reporting consistent with Part 3 of this Schedule which shows that the value of enrolments in eligible training places in the jurisdiction has reached a minimum of 50 per cent of the Fee-Free Construction expenditure as set out in Table 1b. | Estimated for March 2026 |  | * 50 per cent payment for 50 per cent of funding utilised (contingent also on adherence to reporting requirements) * 50 per cent of ancillary funding |

|  |  |  |
| --- | --- | --- |
| **Part 3: Reporting requirements** |  | |
| **Reporting underpinning the Milestones at Part 2.** |  | **Due** |
| For the FFT Fund, States will provide a quarterly report consistent with Appendix E on:   * **Training uptake by quarter** with enrolments, commencements, completions and committed funding to date * **Demographics** of cumulative enrolments, commencements, and completions by agreed target cohorts to date. * **RTO Summary** of training providers by type (TAFE/Dual Sector/Private), including numbers and cumulative enrolments. * **RTO level data** (where the required RTO level data is not available the Commonwealth may agree to modified reporting arrangements) including: * RTO Name, RTO Code, RTO Sector (TAFE/Dual Sector/Private), course name, course code, course type, number of allocated places; and * Training uptake by RTO including cumulative enrolments, commencements, completions and committed funding. * **Course** **level data** of cumulative training uptake including course name, course code, course type, price (existing training place), price (additional training place), and cumulative enrolments, commencements, completions, committed funding, and, where available, student cohorts. |  | * By the 15th day of the month following the end of the quarter for the life of the agreement, unless alternative arrangements agreed in implementation plan. |
| **Mid-Fund Report**  The States will provide a report of progress, including demand for training and any changes in the health and/or economic environment, to inform any required adjustments including to the scope, size, timing and payment structure under the FFT Fund, to help inform the development of the next agreement. |  | * 15 July 2023 |
| **End of Fund Report**  The States will provide an End of Fund Report which provides a stocktake and acquittal, including a review of the Fund and an assessment of its effectiveness in meeting the needs of the target cohorts within, each jurisdiction.  The Commonwealth will collaborate with States on the evaluation of the outcome of the initiative. | * 31 July 2024 | |
| For the **TAFE Technology Fund**, the responsible jurisdiction will provide:  - quarterly progress reports against the individual Project Plan(s) - a final acquittal report on completion of the project. | • By the 15th day of the month following the end of the quarter for the life of the agreement on completion of the project. | |
| For **VET Student Loans**, the Commonwealth will:   * consult States on the development of the draft 2024 course list; and * provide the States with more data on the courses and profile of learners participating in VSL in their jurisdiction. | * From July 2023 (with the list to take effect   1 January 2024)   * April 2023 and April 2024 | |
| **With respect to FFTT2 States will provide:** | | |
| **Report** | **Due** | |
| **Quarterly Reporting** States will continue to provide quarterly reports by the 15th day of the month following the end of the quarter for the life of this Agreement using the Fee-Free TAFE Tranche 1 agreed templates at Appendix E, unless alternative arrangements are agreed in the Implementation  Plan.  States will also report on tuition fee savings (actual or estimated where not available) for students enrolled in FFTT2. Reporting arrangements may be revised once the transition to a new VET Information Standard and new reporting pathways is completed. | • By the 15th day of the month following the end of the quarter for the life of this Agreement unless alternative arrangements are agreed in Implementation Plans. | |
| **Insights Report:** States will provide a review of progress, including demand for training and any changes in the economic environment. The review will also include an assessment of the effectiveness of Fee-Free TAFE Tranche 1 and 2 in meeting the needs of the target cohorts within each jurisdiction. The Commonwealth will collaborate with States on an evaluation of the initiative, incorporating the Insights Report. This evaluation is expected to be completed before the end of 2025.   Once the evaluation is finalised, the Commonwealth and the States will consider the future of Fee Free TAFE beyond 2026, to be agreed by the Skills and Workforce Ministerial Council (SWMC). | • 28 July 2025 | |
| **End of Fund Report** States will provide an End of Fund Report which provides a stocktake and acquittal, including a review of FFTT2, and an assessment of its effectiveness in meeting the needs of the target cohorts within each jurisdiction. The Commonwealth will collaborate with States on the evaluation of the outcome of the initiative. | • 29 June 2027 | |

|  |  |
| --- | --- |
| **With respect to Fee-Free Construction, States will provide:** |  |
| **Report** | **Due** |
| **Quarterly Reporting** States will continue to provide quarterly reports by the 15th day of the month following the end of the quarter for the life of this Agreement using the   Fee-Free TAFE Tranche 2 agreed templates at Appendix E, unless alternative arrangements are agreed in the Implementation Plan.  States will report and identify new places for Fee-Free Construction as part of quarterly reporting. Reporting arrangements may be revised once the transition to a new VET Information Standard and new reporting pathways is completed. | * By the 15th day of the month following the end of the quarter for the life of this Agreement unless alternative arrangements are agreed in Implementation Plans. |
| **Insights Checkpoint** As part of Quarter 4 reporting for 2025, States will provide an update on progress, including insights on demand for training, capacity of training organisations to deliver new places and any changes in the economic environment. | * January 2026 |
| **End of Fund Report** States will provide an End of Fund Report which provides a stocktake and acquittal, including a review of Fee-Free Construction and an assessment of its effectiveness in delivering sector specific places, the impact on other sectors, as well as to meet the needs of the target cohorts within each jurisdiction. The report should be included as part of the FFTT2 End of Fund Report.  The Commonwealth will collaborate with States on the evaluation of the outcome of the initiative. | * 29 June 2027 |

The Parties have confirmed their commitment to this agreement as follows:

|  |  |  |
| --- | --- | --- |
| Signed for and on behalf of the Commonwealth of Australia by    The Hon Andrew Giles MP  Minister for Skills and Training  …../…../2024 |  |  |
| Signed for and on behalf of the  State of New South Wales by    The Hon Steven Whan MP  Minister for Skills, TAFE and Tertiary Education  …../…../2024 |  | Signed for and on behalf of the State of Victoria by    The Hon Gayle Tierney MLC  Minister for Skills and TAFE  …../…../2024 |
| Signed for and on behalf of the State of Queensland by    The Hon Lance McCallum MP  Minister for Training and Skills Development  …../…../2024 |  | Signed for and on behalf of the State of Western Australia by    The Hon Simone McGurk MLA  Minister for Training and Workforce Development  …../…../2024 |
| Signed for and on behalf of the State of South Australia by    The Hon Blair Boyer MP  Minister for Education, Training and Skills  …../…../2024 |  | Signed for and on behalf of the State of Tasmania by    The Hon Felix Ellis MP  Minister for Skills and Training  …../…../2024 |
| Signed for and on behalf of the Australian Capital Territory by    Mr. Chris Steel MLA  Minister for Skills and Training  …../…../2024 |  | Signed for and on behalf of the Northern Territory by    The Hon Gerard Phillip Maley  Minister for Skills, Training and International Education  …../…../2024 |

Appendix A: Funding Principles for the Fee-Free TAFE Fund (FFT Fund)

Priority Learners

1. States will administer learner eligibility for Fee-Free TAFE, prioritising groups including First Nations Australians, young people (17-24), people out of work or receiving income support, unpaid carers, women facing economic insecurity, women undertaking study in non-traditional fields, people with disability and certain categories of visa holders.
   * 1. In this context, States will in local eligibility arrangements in their Implementation Plans and how Fee Free TAFE will be marketed in the first instance to the priority groups.
     2. States will outline the proposed learner eligibility in the Implementation Plan and advise on any changes in quarterly progress reports.

Training in scope of funding

1. Commencing 1 January 2023, the national target for the Fund is 180,000 Fee-Free TAFE places, including 15,000 aged care places (see definitions for Fee-Free and TAFE below). The total indicative numbers of Fee-Free TAFE places, and aged care places, in each jurisdiction in 2023 will be outlined in the State’s Implementation Plan.
2. States will determine the courses (accredited qualifications and short courses) to be funded under this Schedule, to deliver national and/or State-based priorities. National areas of priority include:
   * 1. care (aged care, childcare, health care, disability care);
     2. technology and digital;
     3. hospitality and tourism;
     4. construction;
     5. agriculture; and
     6. sovereign capability (for example manufacturing, and Defence).

1. The States will specify an initial list of courses (qualifications and short courses) covered by this Schedule in their Implementation Plan, which will also address the indicative aggregate of full qualifications and short courses (including micro-credentials), how the list will address national and/or State priority areas, and how the list may be updated.
2. Fee-Free TAFE will be delivered by a registered training provider that is recognised as a TAFE or public dual sector higher education provider, including TAFE auspicing or partnership arrangements. In limited circumstances delivery may also include community training providers or Indigenous training providers where they are better placed to deliver specialist training, as agreed with the Commonwealth in the Implementation Plan.
3. To deliver priority training in the care sector (including 15,000 places nationally in aged care), State delivery may include broader eligibility and qualifications, as agreed with the Commonwealth in the Implementation Plan.
4. The Commonwealth and States may, by exception, agree to specific bilateral training delivery arrangements in the Implementation Plan.
5. Commonwealth Government payments under this Schedule will be directed to State Governments, which will manage the distribution of funds in line with this Schedule and according to their policies and procedures.

Enrolment Period

1. Enrolments for, or delivery commenced from the time of signing this Schedule to 31 December 2023 will be eligible for this Fund, unless varied in the Implementation Plan.

Course Pricing

1. States will use their current pricing policies for VET places in their jurisdiction for setting the price of

Fee-Free TAFE training places. In doing so, they will be informed by advice from Commonwealth Government and State and Territory Government agencies. States’ current pricing policies are subject to change and the price set for the training places under this Schedule may be adjusted through a revised Implementation Plan.

Reporting Arrangements

1. The States will provide reports in accordance with Part 3 aligned with the templates attached to this Schedule.
2. The Commonwealth may share the reports set out in Part 3 with any Commonwealth entity for information, reporting and promotion purposes.

Ancillary Purposes and Student Support Services

1. The State may use up to 10 per cent of the Commonwealth funding contribution for Fee-Free places on (ancillary) costs on a cost shared basis to support the delivery of Fee-Free TAFE and student outcomes. States will not use the Fund for wage subsidies, or major capital works. States will match the ancillary amount and may count existing commitments.
2. The State will also match its (per-capita) allocation of Student Support Services andmay count existing commitments.

Unused funding

1. Where a student enrols in a training place funded through the Fund and then withdraws after the State has received the related milestone payment, the State agrees to redirect that amount back into the Fund to support additional places and associated student supports.
2. Where there is unallocated funding left over from a Commonwealth contribution received by the State at the end of this Fund, States agree to spend any such amount in the TAFE sector.

Promotion of the Fund

1. All governments will take steps to promote access to Fee-Free TAFE training.
2. States and the Commonwealth will make best efforts to ensure they consult on the nature and content of any events, announcements, promotional activity or publicity related to the Fund.

Baseline and matched funding arrangements

1. Consistent with the cost shared arrangements for Fee-Free TAFE, States agree to match the Commonwealth's funding commitment in the 2023 calendar year and not to use FFT Funds to substitute existing expenditure.
2. State contributions may be met through the allocation of funding under existing program streams but must be in addition to the agreed Baseline Funding commitment. States further agree to ensure a proportional increase in funding provided to TAFEs relative to pre-COVID (2019) levels, with this to be agreed with the Commonwealth in the Implementation Plan.
3. The Baseline Funding commitment has been determined by reference to 2019, based on the 2019 NCVER Funding Collection, with adjustments for agreed one-off spending and State funding contributions under Fee-Free TAFE (Table 1 refers).
4. If the Baseline Funding commitment is not met in 2023, Commonwealth payments to States under the new long-term skills funding agreement may be reduced to offset the shortfall in funding. The Commonwealth will not seek to offset shortfalls in funding driven by factors outside the control of States and where States have demonstrated best endeavours to fulfil the Baseline Funding commitment.

**Table 1: State and Territory Baseline funding commitments and additional contributions under the Fee-Free TAFE Fund ($m)**

|  |  |  |
| --- | --- | --- |
|  | Level of baseline funding | Additional Fee-Free TAFE funding |
| New South Wales | 1,099.7 | 155.2 |
| Victoria | 798.3 | 127.8 |
| Queensland | 618.3 | 101.2 |
| Western Australia | 355.7 | 51.8 |
| South Australia | 174.0 | 34.0 |
| Tasmania | 106.2 | 10.4 |
| Australian Capital Territory | 79.8 | 8.3 |
| Northern Territory | 76.6 | 4.7 |

Definitions:

1. For the purposes of this Appendix:
   1. **Ancillary funding** is up to 10 per cent of the value of the Fund**,** to support the delivery of Fee-Free TAFE and student outcomes. This may include wraparound support services to help disadvantaged learners to access training, promotion of Fee-Free TAFE, funding support to assist students in accessing required work placements, or support for learners to access training that is best suited to their needs and the local jobs market and to transition from learning to employment.
   2. **Baseline Funding commitment** means the agreed financial baseline for which additional contributions under the Fund is assessed in 2023.
   3. **Cost shared** means **50:50 cost sharing** between the Commonwealth and the States to deliver Fee-Free TAFE places (including student support) and meet ancillary costs.
   4. **Existing Training Place** means a training place identified by the State as a current place (in agreed priority qualifications and/or for priority learners) where the fee component is met from the Fund*.* States will outline their approach to managing existing places bilaterally.
   5. **Eligible Visa Holders** means a student who holds an eligible visa as agreed between the State and Commonwealth.
   6. **Fee-Free** means the learner will not be charged a fee for the tuition component of training funded through this Fund. Any other fees (e.g., Administration fee or material costs) will be minimal and agreed with the Commonwealth in the Implementation Plan.
   7. **Fee-Free TAFE Fund** includes the Fee-Free TAFE Places fund, ancillary funding and funding for additional support.
   8. **Implementation Plan** is a bilateral plan outlining how Fee-Free TAFE will operate in practice, to be agreed with the Commonwealth. The Implementation Plan template will be provided by the Commonwealth.
   9. **New Training Places** are those where the price of training is fully met from the Fund.
   10. **Student Support Services** means services that enhance student access to training and supporting completions. These will be agreed bilaterally and included in State Implementation Plans.
   11. **TAFE** means a training provider that is recognised as a TAFE, public dual sector higher education provider, a TAFE auspicing or partnership arrangement.

Appendix B: The TAFE Technology Fund

Overview

1. The States acknowledge the Commonwealth has announced a $50 million TAFE Technology Fund, including a number of specific projects across the country to be delivered as a priority.
2. The States agree to work bilaterally with the Commonwealth on the administration of the Fund.
3. In respect of Committed Projects, Implementation Plans will be agreed with the Commonwealth from 31 March 2023.
4. In relation to access to the remaining TAFE Technology Funding Pool, TAFE infrastructure project proposals (projects) will be assessed by the Commonwealth on a competitive basis against the following:

Criterion A: Value for money.

Criterion B: Contribution to improving training delivery standards expected by industry.

Criterion C: Evidence of industry support.

Criterion D: Demonstrable need identified in the State or Territory TAFE sector.

Criterion E: Ability to deliver.

Criterion F: History of capital support for addressing the need.

1. Comprehensive Fund Guidelines and templates will be provided to States (and published).

Cost Sharing Arrangement

1. There is no requirement for States and Territories to match TAFE Technology Funding.

Definitions

1. For the purposes of this Appendix:
   1. **The TAFE Technology Fund** is a $50m Australian Government fund to improve IT facilities, workshops, laboratories, and tele-health simulators across the country.
   2. **Committed Projects** are 14 projects valued at $28.2 million which will be delivered as a priority from the TAFE Technology Fund.
   3. The TAFE Technology **Funding Pool** is $21.8 million which States can apply to access.

Appendix C: Provision of seed funding for VET data Infrastructure Reforms.

Overview

1. $6.85 million has been allocated nationally to support jurisdictions with a funding contribution to undertake impact assessment and cost planning, technical design, sector coordination, implementation and rollout activities associated with implementation of the VET Data Streamlining (VDS) Program during 2023.
2. These funds are a contribution toward the State undertaking VDS transition planning by the end of 2023.
3. Funding has been notionally allocated to jurisdictions as outlined in Table 4.
4. Milestone payments will be made in accordance with Part 2.

Cost Sharing Arrangement

1. There is no requirement for States to match this funding.

Definitions

1. For the purposes of this Appendix:

a. The **VET Data Streamlining** Program is focussed on improving the collection and use of VET activity data. The program aims to introduce:

* 1. a modern technology that enables near real-time submission of VET activity data;
  2. a VET Information Standard to replace the existing Australian Vocational Education and Training Management Information Statistical Standard (AVETMISS); and
  3. updated regulatory and governance settings.

Appendix D: Principles for cost sharing under the VET Student Loans Program

Overview


1. The Commonwealth and the States agree to the VET Student Loans (VSL)Program cost sharing arrangement (below) from 1 January 2023 to 31 December 2023, unless alternative arrangements are bilaterally agreed.
2. This arrangement will cover enrolments from 1 July 2022 to 31 December 2023.
3. This arrangement is limited to loans provided to State subsidised students for courses at the Diploma and Advanced Diploma level.

Cost Sharing Arrangement

1. Each jurisdiction will contribute 50 per cent of the cost of the:
   1. *Debt Not Expected to be Repaid* (***DNER***). The DNER rate will be set at 22 per cent of the value of loans issued in a jurisdiction to its State-subsidised students; and
   2. *Deferral Adjustment Costs* for those loans, arising from the concessional treatment that applies to VSL.
2. The Commonwealth will waive the 20 per cent loan fee for State subsidised students who access a VSL.
3. The Commonwealth will issue invoices in April each year for the calendar year prior.
4. At the time of invoicing, the Commonwealth will provide data on the jurisdiction’s subsidised loans issued by each provider in their jurisdiction for the calendar year prior, including enrolments and loan values.

Definitions

1. For the purposes of this Appendix:
   1. **Debt Not Expected to Be Repaid (DNER)** means loans that are not expected to be repaid due to the income contingent nature of the VSL program. The AGA has modelled the rate of DNER for VSL and advised that a DNER rate of 22 per cent be used for the purposes of cost sharing until the modelling is reviewed again in 2024.
   2. **Deferral Adjustment Costs** means the represented cost of deferring the repayment of the debt and recognises that debts are charged interest broadly in line with the change in the CPI each year, which is different to the underlying cost of government borrowing. The Australian Government Actuary will determine the deferral adjustment rate.

Appendix E: Fee-Free TAFE Reporting Schedule

A close-up of a document

Description automatically generated

A screenshot of a computer

Description automatically generated

A yellow and black rectangular object with black text

Description automatically generated

A screenshot of a spreadsheet

Description automatically generated

# Appendix F: Funding Principles for Fee-Free TAFE Tranche 2

## Priority Learners

1. States will administer learner eligibility for FFTT2 as described in their Implementation Plan, prioritising cohorts including First Nations Australians, young people (17-24), people out of work or receiving income support, unpaid carers, women facing economic insecurity, women undertaking study in non-traditional fields, people with disability and certain categories of visa holders.

1. In this context, States will continue to ensure priority groups are incorporated in local eligibility arrangements and continue marketing FFTT2 to those priority groups.
2. States will advise on any changes to eligibility through their quarterly reports.

## Training in scope of funding

1. States will continue to determine the courses (accredited qualifications and short courses) to be funded under this Agreement to deliver national priorities. Funding under this Agreement for State-based priorities will be agreed in implementation plans. National areas of priority are:
   * care (aged care, childcare, health care, disability care)
   * technology and digital
   * hospitality and tourism
   * construction
   * agriculture, and
   * sovereign capability (for example manufacturing, and defence).
2. The VET Workforce will be included as a new national priority from 1 January 2024
3. States will provide estimates of the number of places for each national priority in their Implementation Plans, based on previous delivery patterns. These numbers will be indicative of expected demand.
4. A focus on these priority sectors would not preclude allocation to other priority skill shortage areas as identified and agreed through SWMC.
5. FFTT2 will be delivered by registered training providers recognised as a TAFE or public dual sector higher education provider, including TAFE auspicing or partnership arrangements. In limited circumstances delivery may continue to include community training providers or Indigenous training providers where they are better placed to deliver specialist training, as agreed within Implementation Plans.
6. The Commonwealth and States may, by exception, agree to specific bilateral training delivery arrangements through Implementation Plans.
7. Commonwealth Government payments under this Agreement will be directed to State Governments, which will manage the distribution of funds in line with this Agreement and according to their policies and procedures.

Enrolment Period

1. Enrolments from the time of signing this Deed of Variation to 31 December 2026 will be eligible unless varied in Implementation Plans.

## Course Pricing

10. States will use their current pricing policies to set the price of FFTT2 training places. In doing so, they will be informed by advice from Commonwealth Government and State and Territory Government agencies. States’ current pricing policies are subject to change and the price set

for the training places under this Agreement may be adjusted through a revised Implementation Plan.

Reporting Arrangements

1. The States will provide reports in accordance with Part 3 aligned with the reporting templates provided through the Agreement, in addition to new quarterly reports on savings (estimated or equivalent) for students enrolled in FFTT2.
2. The Commonwealth may share reports set out in Part 3 with any Commonwealth entity for information, reporting and promotion purposes.

Unused funding

1. Where a student enrols in a training place funded through FFTT2 and then withdraws after the State has received the related milestone payment, the State agrees to redirect that amount back into FFTT2 to support additional places.
2. Where there is unallocated funding left over at the end of 2026, States agree to invest any such amount in Fee-Free TAFE beyond 2026, where practicable, in line with the intent of this Agreement. Where this is not practicable, any such funds will be invested into delivery of TAFE courses.

## Promotion of FFTT2

1. All governments will take steps to promote access to Fee-Free TAFE training.
2. States and the Commonwealth will make best efforts to ensure they consult on the nature and content of any events, announcements, promotional activity, or publicity related to FFTT2. Definitions:
3. For the purposes of this Agreement and FFTT2:
   1. **Existing Training Place** means a training place identified by the State as a current place in agreed priority qualifications and/or for priority learners, where the tuition fee component is met from the Fund*.* States will outline their approach to managing existing places bilaterally.
   2. **Implementation Plan** is a bilateral plan outlining how FFTT2 will operate in practice, to be agreed with Commonwealth skills officials. The Implementation Plan template will be provided by the Commonwealth.

## Fee-Free TAFE Tranche 2 Reporting Schedule

A formal reporting template for the new data set of student cost savings will be supplied.

# Appendix G: Funding Principles for Fee-Free Construction

## Priority Learners

1. States will administer learner eligibility for Fee-Free Construction, as described in their Implementation Plan, prioritising cohorts including First Nations Australians, young people (17-24), people out of work or receiving income support, unpaid carers, women facing economic insecurity, women undertaking study in non-traditional fields, people with disability and certain categories of visa holders:
2. In this context, States will continue to ensure priority groups are incorporated in local eligibility arrangements and continue marketing Fee-Free Construction to those priority groups; and
3. States will advise of any changes to eligibility through their quarterly reports.

## Training Places

1. Commencing 1 January 2025, the national target is 20,000 Fee-Free Construction places, including up to 5,000 pre-apprenticeships.
2. The total indicative numbers of Fee-Free Construction places in each jurisdiction in 2025 and 2026 calendar years will be outlined in the State’s Implementation Plan.
3. States will provide estimates of the number of places for each course to be agreed in their Implementation Plans, based on previous delivery patterns and/or jurisdictional need. These numbers will be indicative of expected demand.

## Training in Scope of Funding

1. States will determine courses (accredited qualifications and short courses) to be funded under this Agreement that are relevant to the construction sector.
2. States will specify an initial list of courses (accredited qualifications and short courses) covered by this Schedule in their Implementation Plan, which will also address the indicative aggregate of full qualifications, short courses and pre-apprenticeships, how the list will service the Construction sector, and how the list may be updated.
3. The Commonwealth and States may by exception agree to specific bilateral training delivery arrangements through Implementation Plans.

## Pre-Apprenticeships

1. Pre-apprenticeships can provide students the opportunity to experience working within a specific industry and may include, but are not limited to, the following features:
   1. nationally recognised training products, with strong links to construction apprenticeship pathways;
   2. a pathway into an Australian Apprenticeship or to additional/alternative training;
   3. availability of wrap-around student support services to support students into prospective employment or apprenticeship opportunities; and/or
   4. involve Group Training Organisations and industry to support access to employment opportunities in the construction sector.

## Training Providers

1. Training providers delivering the new Fee-Free construction places will be agreed through Implementation Plans and predominantly include TAFE or public dual sector higher education providers as well as a mix of private registered training organisations and/or TAFE auspice or partnership arrangements.
2. Delivery of up to 5,000 pre-apprenticeships will be through TAFEs and registered training providers, including partnerships with Group Training Organisations, as agreed in bilateral Implementation Plans.

## Enrolment Period

1. Enrolments from the time of signing this Schedule to 31 December 2026, will be eligible unless varied in Implementation Plans.

## Course Pricing

1. States will use their current pricing policies to set the price of Fee-Free Construction training places. In doing so, they will be informed by advice from the Commonwealth Government and State and Territory government agencies. States’ current pricing policies are subject to change and the price set for the training places under this Agreement may be adjusted through a revised Implementation Plan.

Reporting Arrangements

1. The States will provide reports in accordance with Part 3 aligned with the reporting templates provided through the Agreement for Fee-Free TAFE Tranche 2, for students enrolled in Fee-Free Construction, including identifying and reporting on places for Fee-Free Construction.
2. The Commonwealth may share reports set out in Part 3 with any Commonwealth entity for information, reporting and promotion purposes.

Funding and Unused funding

1. Commonwealth Government payments under this Agreement will be directed to state governments, which will manage the distribution of funds in line with this Agreement and according to their policies and procedures.
2. Where a student enrols in a training place funded through Fee-Free Construction and then withdraws after the State has received the related milestone payment, the State agrees to redirect that amount back to support additional places under this Agreement.
3. Where there is unallocated funding at the end of 2026, States agree to invest any such amount in Fee-Free Construction, where practicable, in line with the intent of this Agreement. Where this is not practicable, any such funds will be invested into delivery of courses relevant to the construction sector.

Promotion of Fee-Free Construction

1. All governments will take steps to promote access to Fee-Free Construction funding.
2. States and the Commonwealth will make best efforts to ensure they consult on the nature and content of any events, announcements, promotional activity, or publicity related to Fee-Fee-Free Construction.

Additionality arrangements

1. Through Implementation Plans, States will nominate a baseline of activity for Fee-Free Construction places, negotiated bilaterally with the Commonwealth.
2. During each calendar year, Fee-Free TAFE Tranche 1 and 2 reported data will be used to compare uplift for Fee-Free Construction enrolments.

Definitions:

For the purposes of the Fee-Free Construction Agreement:

* 1. **Additionality/Additionality arrangements** are enrolments above the State nominated baseline.
  2. **Ancillary funding** is to support the delivery of Fee-Free Construction and student outcomes. This may include wraparound support services to help disadvantaged learners to access training, promotion of Fee-Free Construction, funding support to assist students in accessing required work placements, or support for learners to access training that is best suited to their needs and the local jobs market and to transition from learning to employment.
  3. **Fee-Free** means the learner will not be charged a fee for the tuition component of training. Any other fees (e.g. administration fee or material costs) will be minimal and agreed with the Commonwealth in the Implementation Plan.
  4. **Fee-Free construction places** refers to enrolments in courses and pre-apprenticeships relevant to the construction sector.
  5. **Group training organisation (GTO)** is a corporation established predominately to provide training and employment opportunities. GTOs employ apprentices and trainees and are responsible for ensuring that those employees receive suitable training and experience.
  6. **Implementation Plan/Fee-Free Construction Implementation Plan** is a bilateral plan outlining how Fee-Free Construction will operate in practice, to be agreed with Commonwealth skills officials. The Implementation Plan template will be provided by the Commonwealth.
  7. **New Training Places** (construction) is a training place identified by the State as a new fee-free place that increases the number of places available for a course (in Construction). States will outline their approach to managing new places bilaterally.
  8. **Pre-apprenticeship** means entry level training that also provide students exposure to the Construction industry, and which may pathway into an apprenticeship.
  9. **Registered Training Organisation (RTO)** is registered with ASQA in accordance with the requirements of the VET Quality Framework, to provide specific vocational education and training and/or assessment services.
  10. **Student Support Funding** is to enhance student access to training and improve completions. These activities will be agreed bilaterally and included in State Implementation Plans.
  11. **TAFE** means a training provider that is recognised as a TAFE, public dual sector higher education provider, a TAFE auspicing or partnership arrangement.
  12. **Visa Holders** means a student who holds an eligible visa as agreed between the State and Commonwealth.