# Schedule B

Stage 1 Funding for Victorian Supply Measures-Environmental Works Program

**Project Agreement for Stage 1 funding for SUSTAINABLE DIVERSION LIMITS (sdl) ADJUSTMENT Supply and constraints Measures in the Murray-Darling Basin**

* 1. This Schedule has been developed in accordance with Clause 18 of the Project Agreement for Stage 1 Funding for Sustainable Diversion Limits (SDL) Adjustment Supply and Constraints Measures in the Murray-Darling Basin [the Agreement].
	2. This Schedule will commence as soon as it is agreed between the Commonwealth and Victoria and will expire on 31 December 2023, or on completion of agreed activities, including final performance reporting and processing of final payments against milestones.
	3. The Commonwealth will provide an estimated total financial contribution to Victoria of up to $120.3 million in respect of this Schedule as shown in Table 1. All payments are GST exclusive.

**Table 1: Estimated financial contributions**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **($ million)** | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | Total |
| **Estimated total budget** | **1.6** | **11.1** | **16.3** | **28.8** | **59.2** | **3.3** | **120.3** |
| Less estimated National Partnership Payments | 1.6 | 11.1 | 16.3 | 28.8 | 59.2 | 3.3 | 120.3 |
| Balance of non-Commonwealth contributions | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 |

* 1. The parties acknowledge that a variation to this Schedule was agreed in 2019-20, which rescheduled some activities and included other new activities in the milestones pending clarity on the regulatory approval requirements. The parties acknowledge that a second variation was agreed in 2020-21, which incorporated the regulatory approval requirements and included the finalisation of the deferred activities. The parties also acknowledge that a third variation was agreed in 2022-23, which addresses cost pressures from COVID-19 and inclement weather conditions delaying field survey completion work required for the regulatory approvals process. This variation also incorporates acceleration of pre-construction activities such as commencement of long-lead procurement items.
	2. The Stage 1 activities or outputs to be delivered by Victoria are outlined below:
		1. the Victorian Basin Plan Environmental Works Program delivery strategy for the implementation of nine environmental works supply measures, Belsar-Yungera, Burra Creek, Hattah Lakes North, Nyah, Lindsay Island, Vinifera, and Wallpolla Island Floodplain Management Projects and the Guttrum and Benwell State Forests and Gunbower National Park Floodplain Environmental Works Projects. This work includes:
			1. producing the Victorian Basin Plan Environmental Works Program delivery strategy document and establishing the program governance framework and program team;
			2. engaging specialist resources including service level agreements with the Mallee and North Central Catchment Management Authorities (CMA), Goulburn Murray Water (GMW), Lower Murray Water (LMW) and Parks Victoria (PV) and engaging engineering consultancy firm (s) as the Owner’s Engineer;
			3. completing project management plans for the program of works;
			4. preparing draft native fish management plans for seven of the measures and a regional native fish discussion paper; and
			5. producing a final consolidated business case for the nine measures.
		2. Stage 1 activities for the nine environmental works supply measures including:
			1. preparing concept, functional and detailed designs;
			2. lodging key environmental referrals
			3. producing an updated regulatory approvals strategy, post referral outcome for each measure including, but not limited to the following information:
1. confirmation of referral outcome and costings to obtain key environmental referrals and other heritage and planning statutory approvals with approving authorities;
2. timeline to complete all preconstruction activities for each measure including the production of a final Stage 2 Implementation Proposal and confirmation of the submission of the measures to the Commonwealth for gateway assessment, and detailed designs for remaining measures; and
3. commencement of post referral activities for Hattah Lakes North, Nyah and Vinifera.
	* + 1. producing Draft and Final Stage 2 implementation proposals for each measure including, but not limited to the following information:
				1. confirmation of the submission of the measures to the Commonwealth for gateway assessment;
				2. Stage 2 cost estimate for the measures;
				3. evidence to demonstrate resolution, or a strategy to resolve all issues identified in the assessment of the business cases for the measures for the SDL adjustment mechanism and recorded in the Post-Phase 2 Issues Register; and
				4. arrangements for ongoing ownership and responsibility for operations and maintenance costs for the measures.
				5. confirmation that the measures have received all necessary statutory approvals.
				6. option agreements for creating flood easements, sourcing clay material, undertaking works, and allowing future access on privately owned land in place.
				7. tendering of the construction works with award being subject to conditions precedent of approval of Stage 2 funding.
				8. baseline ecological, social and economic monitoring in place.
	1. In accordance with the Agreement, Victoria will provide reports on the progress of each output in accordance with the timing in Table 2. If a report referred to in Table 2 indicates that Victoria has not met the relevant milestone, Victoria may submit a later report demonstrating that the relevant milestone has been met, for the purposes of clause 21 of the Agreement. In addition to the reporting specified in the Agreement, the reports to be provided by Victoria will include:
		1. Stage 1 Activities Status Update outlining activities completed in the current period that progress achievement of subsequent milestones, including details of any costs incurred in completing the activities, consistent with clause 29 of the Agreement;
		2. a project risk register update;
		3. a stakeholder consultation update; and
		4. updates on resolution of the issues identified during the assessment of the business cases for the measures listed in clause 4 of this Schedule and reflected in the Post-Phase 2 Issues Register.
	2. In accordance with clause 21 of the Agreement the milestones for activities, their relationship to the outputs, relevant reporting dates and the maximum expected payments to be made are set out in Table 2. The guideline on items to be addressed by Victoria in the delivery of milestones is at Appendix 1.

**Table 2: Milestones, reporting and payment summary**

| No. | **Outputs** | **Milestones**  | **Report Due**  | **Payment (up to amount)** |
| --- | --- | --- | --- | --- |
| 1 | **1.1) Victorian Basin Plan Environmental Works Program delivery strategy, governance and resources** | Completion of Program Delivery Strategy, establishment of program governance and start-up team.Completion of draft project plans and service level agreement template. Concept designs confirmed and draft fish management plans completed for seven project sites and a regional native fish discussion paper. Request for Tender (RFT) for owner’s engineer finalised and ready for release to market and communications and stakeholder engagement strategy completed. | 31 March 2019 | $1,566,670 (milestone completed - paid) |
| 2 | **2.1) Victorian Basin Plan Environmental Works Program delivery strategy, governance and resources** | Engagement of specialist resources, finalisation of service level agreements and project plans, recruitment of full program team (for stage 1), communications and stakeholder engagement progress report and the completion of a final consolidated business case for the nine environmental works supply measures.  | 30 September 2019 | $2,442,906(milestone completed – paid) |
| **2.2) Gunbower National Park Floodplain Management Project** | Completion of Concept Design for Gunbower | 30 September 2019 |
| **2.3) Guttrum and Benwell State Forests Floodplain Environmental Works Project** | Completion of Concept Design for Guttrum and Benwell | 30 September 2019 |
| **2.4) Hattah Lakes North Floodplain Management Project** | Completion of detailed design reports. Lodgement of key environmental referrals with approving authorities. Completion of Draft Stage 2 implementation proposal.  | 30 September 2019 |
| 3 | **3.1) Belsar-Yungera Floodplain Management Project** | Completion of functional design reports  | 31 March 2020 | $8,692,714 (milestone completed – paid) |
| **3.2) Guttrum and Benwell State Forests Floodplain Environmental Works Project** | Completion of functional design reports  | 31 March 2020 |
| **3.3) Lindsay Island Floodplain Management Project** | Completion of functional design reports  | 31 March 2020 |
| **3.4) Nyah** **Floodplain Management Project** | Completion of functional and detailed design reports.Lodgement of key environmental referrals with approving authorities. Completion of Draft Stage 2 implementation proposal. | 31 March 2020 |
| **3.5) Vinifera Floodplain Management Project** | Completion of functional and detailed design reports. Lodgement of key environmental referrals with approving authorities. Completion of Draft Stage 2 implementation proposal. | 31 March 2020 |
| 4 | **4.1) Belsar-Yungera Floodplain Management Project** | Lodgement of key environmental referrals with approving authorities. Completion of Draft Stage 2 implementation proposal. | 30 September 2020 | $9,113,379(milestone completed - paid) |
|  | **4.2) Burra Creek Floodplain Management Project** | Completion of functional design reports  | 30 September 2020 |
|  | **4.3) Gunbower National Park Floodplain Management Project** | Completion of functional design reports  | 30 September 2020 |
|  | **4.4) Guttrum and Benwell State Forests Floodplain Environmental Works Project**  | Lodgement of key environmental referrals with approving authorities. Completion of Draft Stage 2 implementation proposal. | 30 September 2020 |
|  | **4.5) Lindsay Island Floodplain Management Project** | Lodgement of key environmental referrals with approving authorities. Completion of Draft Stage 2 implementation proposal. | 30 September 2020 |
|  | **4.6) Wallpolla Island Floodplain Management Project** | Completion of functional design reports  | 30 September 2020 |
| 5 | **5.1) Victorian Basin Plan Environmental Works Program delivery strategy, governance and resources** | Completion of an updated regulatory approvals strategy (post-referral outcome), and progression of cultural heritage approval activities and post-referral approvals scoping for each of the nine measures. | 31 March 2021 | $90,000(milestone completed - paid) |
| **5.2) Burra Creek Floodplain Management Project** | Lodgement of key environmental referrals with approving authorities.Completion of Draft Stage 2 implementation proposal. | 31 March 2021 | $1,520,000(milestone completed - paid) |
| **5.3) Gunbower National Park Floodplain Management Project** | Lodgement of key environmental referrals with approving authorities.Completion of Draft Stage 2 implementation proposal. | 31 March 2021 | $1,600,000(milestone completed - paid) |
| **5.4) Wallpolla Island Floodplain Management Project** | Lodgement of key environmental referrals with approving authorities.Completion of Draft Stage 2 implementation proposal. | 31 March 2021 | $3,974,331(milestone completed - paid) |
|  | **5.5) Regulatory Approvals, detailed designs, land dealings, construction tendering and baseline monitoring, evaluation and reporting** | **Project Delivery*** Preparation of Master Schedule for the delivery of the regulatory approval activities

**Regulatory Approvals*** + Establishment of Technical Reference Group (TRG)
	+ Completion of final EES and ER/PSA Study Programs
	+ Submission of EES and ER/PSA Scoping Requirements to TRG
	+ Completion of draft EES and ER/PSA Project Description Chapters
	+ Completion of Spring 2020 Ecology Field Investigations
	+ Completion of standard CHMP reports

**Procurement*** Execution of Panel contracts with Environmental & Planning Approvals consultants.
* Issuing of Service Orders for the preparation of impact assessments

**Monitoring, Evaluation & Reporting*** Procurement of services to collect benchmark MER data
 | 31 March 2021\* | $10,372,024(milestone completed - paid) |
| 6 | **6) Regulatory Approvals, detailed designs, land dealings, construction tendering and baseline monitoring, evaluation and reporting** | **Regulatory Approvals*** + Completion of draft EES Introduction Chapters
	+ Completion of draft ER/PSA Introduction Chapters
	+ Completion of Summer 2020/21, Autumn 2021 and Winter 2021 Ecology Field Investigations
	+ Completion of Surface Water and Groundwater draft EES and ER/PSA Specialist Assessments
	+ Completion of draft complex CHMP reports

**Procurement*** + Completion of Procurement strategy for Early Tender Involvement
	+ Release of tender to the open market for Early Tenderer Involvement (ETI) construction procurement.
 | 30 September 2021 | $18,421,598(milestone completed - paid) |
| 7  | **7) Regulatory Approvals, detailed designs, land dealings, construction tendering and baseline monitoring, evaluation and reporting** | **Regulatory Approvals****ER Central:*** Draft of Introductory Chapters (Volume 1)
* Draft of Effects Chapters (Volume 2)
* Draft of Environmental Management Framework (Volume 3)
* Draft of Technical Specialists Assessments (Volume 5)

**ER East:*** Draft of Introductory Chapters (Volume 1)
* Draft of Technical Specialists Assessments (Volume 5)

**EES Central:*** Draft of Introductory Chapters (Volume 1)
* Draft of Effects Chapters (Volume 2)
* Draft of Environmental Management Framework (Volume 3)
* Draft of Attachments to EES/ER (Volume 4)
* Draft of Technical Specialists Assessments (Volume 5)

**Land Dealings*** + Preparation of draft agreements for all properties requiring land dealings

**Monitoring, Evaluation & Reporting*** + Submission of ecological and socio-economic MER plan
 | 31 July 2022 | $28,706,378 |
| 8a | **8a) Regulatory Approvals, detailed designs, land dealings, construction tendering and baseline monitoring, evaluation and reporting** | **Regulatory Approvals****ER Central:*** Draft of Attachments to EES/ER (Volume 4)
* Finalisation of Environmental Management Framework (Volume 3)
* Finalisation of Technical Specialists Assessments (Volume 5)

**ER East:*** Finalisation of Environmental Management Framework (Volume 3)

**EES Central:*** Finalisation of Introductory Chapters (Volume 1)
* Finalisation of Effects Chapters (Volume 2)
* Finalisation of Environmental Management Framework (Volume 3)
* Finalisation of Technical Specialists Assessments (Volume 5)
* PCG Endorsement of Comms Plan

**EES West:*** Draft of Technical Specialists Assessments (Volume 5)

**Procurement*** + All Packages: ECI Contractors Appointed (Stage 2 Acceleration)

**Monitoring, Evaluation & Reporting*** + Completion of collection of year 1 (Spring 2021 and Autumn 2022) ecological baseline data per MER plan
 | 30 September 2022 |  $10,680,000 |
| 8b | **8b) Regulatory Approvals, detailed designs, land dealings, construction tendering and baseline monitoring, evaluation and reporting** | **Regulatory Approvals****ER Central:*** Finalisation of Introductory Chapters (Volume 1)
* Finalisation of Effects Chapters (Volume 2)
* Finalisation of Attachments to EES/ER (Volume 4)

**ER East:*** Finalisation of Introductory Chapters (Volume 1)
* Finalisation of Effects Chapters (Volume 2)
* Finalisation of Attachments to EES/ER (Volume 4)
* Finalisation of Technical Specialists Assessments (Volume 5)

**EES Central:*** Submission of Draft Complex CH Chapters
* Finalisation of Attachments to EES/ER (Volume 4)

**EES West:*** Draft of Effects Chapters (Volume 2)
* Draft of Introductory Chapters (Volume 1)
* Draft of Environmental Management Framework (Volume 3)

Draft of Attachments to EES/ER (Volume 4)**Procurement*** All Packages: ECI Submission (Final Price) (Stage 2 Acceleration)
* All Packages: Release Tender for CH Salvage Contractor (Stage 2 Acceleration)

**Land Dealings** * All Packages: Option Payment to Landholders (Stage 2 Acceleration)
 | 31 December 2022 | $13,335,000 |
| 9  | **9) Regulatory Approvals, detailed designs, land dealings, construction tendering and baseline monitoring, evaluation and reporting** | **Regulatory Approvals****ER Central:*** Submission of Complex CHMP

**ER East:*** Submission of Complex CHMP

**EES Central:*** Submission of Complex CHMP
* Exhibit Planning Scheme Amendment

**EES West*** Submission of Draft Complex CH Chapters
* Finalisation of Introductory Chapters (Volume 1)
* Finalisation of Effects Chapters (Volume 2)
* Finalisation of Environmental Management Framework (Volume 3)
* Finalisation of Attachments to EES/ER (Volume 4)
* Finalisation of Technical Specialists Assessments (Volume 5)

**Project Delivery*** All Packages: Stage 2 Implementation Plan and Stage 1 -> Stage 2 Transition Plan

**Monitoring, Evaluation & Reporting*** Completion of ecological MER database development bespoke for VMFRP with input of first year (Spring 2021 and Autumn 2022) VMFRP baseline data for all nine sites.
 | 31 March 2023 | $6,410,000 |
| 10  | **10) Regulatory Approvals, detailed designs, land dealings, construction tendering and baseline monitoring, evaluation and reporting** | **Regulatory Approvals****All Packages:*** Submit Secondary Approvals and Management Plans

**ER Central:*** Submission of Planning Scheme Amendment

**ER East:*** Submission of Planning Scheme Amendment

**EES West:*** Submission of Complex CHMP
* Exhibit Planning Scheme Amendment
 | 30 June 2023 | $3,325,000 |
| **Total Commonwealth Funding** | **$120,250,000** |

 \*Payment for milestone 5.5 was not made until 7 February 2022

**Table 3: Summary of available funding for each milestone period**

|  |  |  |
| --- | --- | --- |
| Period Number | Period | Available funding,up to amount |
| 1 | Upon signing to 30 Mar 2019 | $1,566,670 |
| 2 | 1 Apr 2019 to 30 Sep 2019 | $2,442,906 |
| 3 | 1 Oct 2019 to 31 Mar 2020 | $8,692,714 |
| 4 | 1 Apr 2020 to 30 Sep 2020 | $9,113,379 |
| 5 | 1 Oct 2020 to 30 Sep 2021 | $17,556,355 |
| 6 | 1 Sep 2021 to 28 Feb 2022 | $18,421,598 |
| 7 | 1 Mar 2022 to 31 Jul 2022 | $28,706,378 |
| 8a | 1 Aug 2022 to 30 Sep 2022 | $10,680,000 |
| 8b | 1 Oct 2022 to 31 Dec 2022 | $13,335,000 |
| 9 | 1 Jan 2023 to 31 Mar 2023 | $6,410,000 |
| 10 | 1 Apr 2023 to 30 Jun 2023 | $3,325,000 |
| **Total** |  | **$120,250,000** |

* 1. Funds will be paid for actual expenditure incurred for the achievement of project milestones. Payments may also include amounts for costs incurred on activities completed in the current period that progress achievement of subsequent milestones.
	2. Expenditure on activities under this Schedule incurred by Victoria from 1 November 2018 to the date of the signing of the first agreement to this Schedule up to $5 million will be eligible for consideration for payment under milestones in this Schedule.
	3. If the actual expenditure for a particular milestone is less than the payment amount for that same milestone, the residual amount (being the difference between the actual expenditure and the payment amount) will remain available under this Schedule as a contingency for meeting any necessary reasonable additional costs for activities under the Schedule subject to the clauses 10 to 14 of this Schedule.
	4. The Commonwealth may agree to requests from Victoria to transfer a residual amount, or part thereof, to a subsequent milestone in the work streams in this Schedule.
	5. A request from Victoria to transfer a residual amount to a milestone falling within the same financial year may be agreed to by the Commonwealth portfolio minister. Such transfers may be agreed and take place without a variation to the Schedule.
	6. The Commonwealth Minister may delegate the agreement of transfers of residual amounts within the same financial year to senior Commonwealth officials, having regard to the financial and policy risks associated with the transfers.
	7. A request from Victoria to transfer a residual amount to increase a milestone amount in a later financial year may be agreed in writing by the relevant Commonwealth and State portfolio ministers in accordance with clause 35 of the Agreement.
	8. Victoria will provide a reconciliation of any residual amounts that have been transferred to subsequent milestones as part of reports required in accordance with clause 23 of the Agreement.
	9. The outputs in Table 2 are independent bodies of work. Milestones and associated payments in one output are independent of milestones and payments in other outputs. The non‑completion of a milestone by its reporting date in a particular output will not prevent payment being made for a completed milestone in a different output.



Appendix 1

Victorian Supply Measures- Environmental Works Program – Guideline on items to be addressed by Victoria in the delivery of Milestones

| Victorian Basin Plan Environmental Works Program delivery strategy, governance and resources |
| --- |
| Milestones | Deliverable | Details of Deliverables |
| Completion of Program Delivery Strategy, establishment of program governance and start -up team. Completion of draft project plans and service level agreement template. Concept designs confirmed and draft fish management plans completed for seven project sites and a regional native fish discussion paper.Request for Tender (RFT) for owner’s engineer finalised and ready for release to market, communications and stakeholder engagement strategy completed.  | Victorian Basin Plan Environmental Works Program (VBPEWP) Delivery Strategy  | * VBPEWP Delivery Strategy document.
* Post-phase 2 business case issues register update
* Regulatory approvals strategy
* Program issues and risk register
* Monthly cashflow forecast
 |
| Establishment of program governance | * Program Control Group (PCG) terms of reference
* List of PCG members
* Program charter
* Template program partner Service Level Agreements (SLAs)
 |
| Program Director and Program Team resourcing  | * Appointment of Interim Program Director
* Resourcing of initial program skeleton team
* Program Director position description
* Program team resourcing plan
* Owner’s engineer procurement strategy
 |
| Financial ring-fencing policy established | * Ring-fencing policy document
* Program chart of accounts
 |
| Service level agreements with agencies | * Specification and scope of works for Mallee CMA, North Central CMA, GMW, LMW and PV
* Paper documenting the roles, responsibilities and membership of Stakeholder Reference Groups and Technical Advisory Groups
 |
| Project plans  | * Program Management Plan
* Quality Management Plan
* Safety Management Plan
* Environmental Management Plan
* Procurement Management Plan
* Risk Management Plan and risk register
* Stakeholder Engagement Plan and schedule
* Cost and Schedule Management Plan
* Finance Management Plan
 |
| Owner’s engineer RFT  | RFT for engaging the Owner Engineer prepared and ready to release to the market. |
| Confirmed Concept Designs and Draft native fish management plans | * Confirmed Concept design reports for seven of the nine project sites
* Seven draft project native fish management plans
* Draft regional native fish discussion paper
 |
| Communications and stakeholder engagement | * Communications and engagement strategy
* Evidence that stakeholder and Traditional Owner engagement has commenced
* Program communications material - websites, fact sheets, social media
 |
| Engagement of specialist resources, finalisation of service level agreements and project plans, recruitment of full program team (for Stage 1), communications, stakeholder engagement progress report, and the completion of a final consolidated business case for the nine environmental works supply measures.  | Owner’s engineer engaged | Executed contract between Program and Owner’s Engineer (s). |
| Program team recruitment, communications and stakeholder engagement  | * Position descriptions for key roles in Stage 1 team
* Evidence that dedicated staff have been engaged to fill positions
* Evidence that Program site office and associated IT equipment are in place
* Establish Program systems and processes required for a major infrastructure program
 |
| Final consolidated business case  | Finalised consolidated business case document including:* updated cost estimate for all nine projects based on current design basis
* integration arrangements
* regulatory approvals strategy
* program master schedule for program delivery to completion
* updated risk and issues register
* works procurement strategy
 |
| Completion of an updated regulatory approvals strategy, post referral outcome, for each of the nine measures. | Final updated regulatory approvals strategy | * Confirmation of referral outcome and costings to obtain key environmental referrals and other heritage and planning statutory approvals with approving authorities
* Timeline to complete all preconstruction activities for each measure including the production of a final Stage 2 Implementation Proposal and confirmation of the submission of the measures to the Commonwealth for gateway assessment, and detailed designs for remaining measures
* Commencement of post referral activities for Hattah Lakes North, Nyah and Vinifera
 |

| Stage 1 activities for nine environmental works supply measures: Belsar-Yungera, Burra Creek, Hattah Lakes North, Nyah, Lindsay Island, Vinifera, and Wallpolla Island Floodplain Management Projects and the Guttrum and Benwell State Forests and Gunbower National Park Floodplain environmental Works Projects  |
| --- |
| Milestones | Deliverable | Details of Deliverables |
| Completion of concept designs  | Concept designs reviewed and confirmed for the nine measures  | * Concept designs reviewed and confirmed for Belsar-Yungera, Burra Creek, Hattah Lakes North, Nyah, Lindsay Island, Vinifera, and Wallpolla Island Floodplain Management Projects
* Concept designs completed for the Gunbower National Park Floodplain Management Project
* Concept designs completed for the Guttrum and Benwell State Forests Floodplain Environmental Works Project
 |
| Completion of functional designs  | Functional designs for each measure  | Functional design reports for the respective measure comprising:* completed geotechnical investigations
* finalised design criteria
* finalised access arrangements
* finalised mechanical-electrical equipment specification
* draft operating regime
* preliminary hydraulic design of assets
* preliminary structural design of assets
* preliminary construction cost estimate
* issued for review (IFR) design drawing package
 |
| Completion of detailed design reports for each measure Lodgement of key environmental referrals and other heritage and planning statutory approvals with approving authorities. Completion of Draft and final Stage 2 implementation proposal | Detailed designs for each measure | Detailed design reports for the respective measure comprising:* preliminary operating regime
* final hydraulic design of assets
* final structural design of assets
* final construction cost estimate
 |
| Project - Environmental Referrals and any other necessary statutory approvals | Key environmental referrals and other heritage and planning statutory approvals for the respective measure lodged with approving authorities  |
| Draft and final Stage 2 implementation proposal for each measure  | Draft and final Stage 2 implementation proposal for the respective measure including, but not limited to the following information:* Confirmation of the submission for the respective measure to the Commonwealth for gateway assessment
* Stage 2 cost estimate for the respective measure
* Evidence to demonstrate resolution, or a strategy to resolve all post-Phase 2 assessment issues for the respective measure
* Arrangements for ongoing ownership and responsibility for operations and maintenance costs for the respective measure
* Confirmation that the measures has received all necessary statutory approvals.
 |