Project Plan

TAFE Centres of Excellence

**FEDERATION FUNDING AGREEMENT – EDUCATION AND SKILLS**

|  |
| --- |
| **Part 1: Formalities and operation of Project Plan** |
| Parties | CommonwealthWestern Australia |
| TAFECentre of Excellence | Clean Energy Skills National Centre of Excellence (CESNCE) |
| Duration | This Project Plan will expire on 31 December 2028 (in line with the National Skills Agreement [NSA]), or on completion of all milestones in Table 2 below, including final performance reporting. |
| Purpose | This Project Plan will support the delivery of the CESNCE. The CESNCE is being established under Part 6 of the NSA.This Project Plan outlines the additional activities funding for the CESNCE through the Turbocharging TAFE Centres of Excellence and Advancing Higher Apprenticeships (Turbocharging) measure. The Turbocharging measure was announced as part of*Working Future: The Australian Government’s White Paper on Jobs and Opportunities*. The purpose of this additional funding is to fast-track the establishment of the CESNCE and to support work to expand the use of higher apprenticeship pathways. |
| Estimated financial contributions | The Commonwealth will provide an estimated total financial contribution to Western Australia of $5.03 million in respect of this Project Plan.

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |

**Table 1****($ million) 2024-25 2025-26 Total****Estimated total budget 2.012 3.018 5.03***Less estimated National Partnership Payments* 2.012 3.018 5.03 Balance of non-Commonwealth contributions 0.0 0.0 0.0 |

|  |
| --- |
| **Table 2: Performance requirements, reporting and payment summary** |
| **Milestone** | **Deliverable/Evidence** | **Estimated milestone delivery****and payment date** | **Payment Value (Commonwealth Funded)** |
| **Milestone 1**Commonwealth agreement to and signing of this Project Plan for the Turbocharging TAFE Centres of Excellence and Advancing Higher Apprenticeships measure for the CESNCE(Turbocharging CESNCE). | Final TAFE Centre of Excellence Schedule Final Turbocharging CESNCE Project Plan | 30 November 2024 For payment by 31 December 2024 | $1.509 million |
| **Milestone 2**Commonwealth acceptance that the CESNCE has:* Initiated consultation on training product design and development and work program (includes Universities, dual sector providers, TAFEs, Jobs and Skills Councils), and
* Developed a marketing and promotional plan and initiated implementation.
 | Report signed by WA senior official with responsibility for skills that outlines key activities of the CESNCE in the reporting period (1 July 2024 to 30 September2024) and attaches:* stakeholder engagement strategy encompassing approach to training product co-design and development, and
* an approved CESNCE marketing and promotional plan and initial implementation activities.
 | 30 November2024 For payment by 31December 2024 | $0.503 million |
| **Milestone 3**Commonwealth acceptance that the CESNCE has:* implemented a State Training Board workforce strategy and roadmap (including infrastructure, facilities, and equipment)
* made changes to *Vocational Education and Training (General) Regulations 2009* (WA) to support AQF 7 qualifications (Reg 6 amended).
* implemented WA Jobs and Skills Employer Incentives
 | Report signed by WA senior official with responsibility for skills that outlines key activities of the CESNCE in the reporting period (1 October 2024 to 30 September2025) and attaches:* State Training Board workforce strategy and roadmap
* amendments to the *Vocational Education and Training (General) Regulations 2009* (WA)
* program documentation for the WA Jobs and Skills Employer Incentive
* program documentation for wrap-around support programs
 | 30 September 2025For payment by 31December 2025 | $3.018 million |

|  |  |  |  |
| --- | --- | --- | --- |
| * put wrap-around support programs co- designed with employers and First Nations in place and contracted delivery partners contracted
* accredited course/s
* cleared occupational licensing, and
* finalised the State Training Board – Industry Training Council higher apprenticeship notice of intent schedule

and commenced a consultation program. | * details of course/s accredited added to the National Training Register
* occupational licensing requirements clearance, and
* finalised higher apprenticeship notice of intent schedule and consultation program report.
 |  |  |

The Parties have confirmed their commitment to this Project Plan as follows:

|  |  |
| --- | --- |
| **Signed** *for and on behalf of the Commonwealth of Australia by***The Honourable Andrew Giles MP**Minister for Skills and Training / / | **Signed** *for and on behalf of the State of Western Australia by***The Honourable Simone McGurk MLA**Minister for Training and Workforce Development / / |