Schedule

Upgrades to the Qtopia Sydney Museum

FEDERATION FUNDING AGREEMENT – INFRASTRUCTURE

|  |  |
| --- | --- |
| **Table 1: Formalities and operation of schedule** | |
| Parties | Commonwealth  New South Wales |
| Duration | This Schedule is expected to expire on 30 June 2027 or when all project deliverables outlined in this Schedule have been completed and acquitted. |
| Purpose | This Schedule will support further upgrades in accordance with the project scope (refer Table 2A) to Qtopia Sydney, a dedicated creative, cultural and education space at the site of the former Darlinghurst Police Station, created as a centre for celebrating and educating on LGBTQIA+ history and culture. |
| Estimated financial contributions | The Commonwealth will provide an estimated total financial contribution to the State of $1.5m in respect of this Schedule.   |  |  |  |  | | --- | --- | --- | --- | | **Table 1**  **($ million)** | **2024-2025** | **2025-2026** | **Total** | | **Estimated total budget** | **4.25** | **7.75** | **12.0** | | *Less estimated National Partnership Payments* | 1.5 | 0.0 | 1.5 | | Balance of non-Commonwealth contributions | 2.75 | 7.75 | 10.5 |   Note: The NSW Government will provide an estimated $10.5m towards the completion of this project. |
| Additional terms | **Funding arrangements**  Consistent with Clause 20a of the *Federation Funding Agreement – Infrastructure,* the State’s role will include forwarding Commonwealth funding contributions to Qtopia Limited, a third party proponent, as necessary to meet the requirements of this Schedule. The State’s role will also include liaising with Qtopia Limited to obtain and submit information or evidence as necessary to support milestone claim requests.  **Commonwealth Funding Recognition**  In addition to the requirements set out in Clause 21 of the *Federation Funding Agreement – Infrastructure,* the Parties agree to:   1. Recognise the Commonwealth’s and State’s funding contribution to the project in publications, promotional and advertising materials, including project signage, and public announcements and activities in relation to the project as appropriate; 2. Provide reasonable opportunity for each Party to contribute to developing communications strategies for the project; and 3. Provide equal access to products that they obtain for use in the development of promotional material for the project, including but not limited to project data, footage and images, subject to any disclosure or usage restrictions (including but not limited to confidentiality or intellectual property restrictions).   **Program meetings and reporting**  The Parties commit to regular communication to support administration of the project in respect of this Schedule. This includes collaborative sharing of information to ensure both Parties are reasonably informed of the status and progress of the project and key issues, in order to perform their roles and responsibilities.  In particular, the Commonwealth and State will participate in quarterly project oversight meetings, with variations to the frequency to be agreed by officials.  Additionally, the State and third-party proponents will provide relevant information on the development and progress of the funded project to the Commonwealth (in accordance with the performance milestones at Table 2B, and occasionally on request, with reasonable notice), and the State will liaise with third-party proponents where required, to assist the Commonwealth with performing its roles and responsibilities. |

|  |  |  |  |
| --- | --- | --- | --- |
| **Table 2A: Project scope and funding commitments** | | | |
| **Project** | **Project Scope** | **Total Commonwealth Contribution** | **Total non-Commonwealth Contribution** |
| **Upgrades to the Qtopia Sydney Museum** | The Project involves the delivery of capital works to upgrade the first floor of the former Darlinghurst Police Station and expand Qtopia Sydney (Qtopia exhibits currently occupy the ground floor). The upgrades to the first floor will include the physical upgrade of the building to meet current construction code requirements (the base build) and the fit out of spaces for Qtopia’s activities including exhibition and creative spaces, storage, and office space. | $1,500,000 | $10,500,000 |

|  |  |  |
| --- | --- | --- |
| **Table 2B: Performance requirements, reporting and payment summary** | | |
| **Performance milestones** | **Report due** | **Payment** |
| **Milestone 1 – Design Consultant and Delivery Partner engaged for base build**   * Execution of contract for Lead Architect for design services for base build * Execution of Co-Funding Partnership Agreement with NSW Public Works 2024-2025 Minister’s Stonework Program | 18/03/2025 | $750,000 |
| **Milestone 2 – Concept design completed and Head Contractor engaged for base build**   * Completion of concept design for base build * Finalisation of exhibition themes and concepts * Formal engagement of NSW Public Works as Delivery Partner for base build | 19/05/2025 | $750,000 |
| **Milestone 3 – Formal progress report accepted by the Australian Government**  Acceptance by the Australian Government of a formal project progress report that includes at a minimum, an update on project costs, timing, key risks, key achievements, public communications and media activities, and progress against milestones. | 15/09/2025 | Nil |
| **Milestone 4 – Formal progress report accepted by the Australian Government**  Acceptance by the Australian Government of a formal project progress report that includes at a minimum, an update on project costs, timing, key risks, key achievements, public communications and media activities, and progress against milestones. | 16/03/2026 | Nil |
| **Milestone 5 – Post-Completion Report accepted and approved by the Australian Government**  Acceptance by the Australian Government of a Project Post-Completion Report that includes at a minimum:   * Details of the use of Australian Government funds, and * Confirmation of all project elements having been delivered and any agreed changes from the initial project scope | 15/08/2026 | Nil |

The Parties have confirmed their commitment to this schedule as follows:

|  |  |  |
| --- | --- | --- |
| Signed for and on behalf of the Commonwealth of Australia by    The Honourable Catherine King MP  Minister for Infrastructure, Transport, Regional Development and Local Government  [Day] [Month] 2025 |  | Signed for and on behalf of the  State of New South Wales by    The Honourable John Graham MLC  Special Minister of State, Minister for Transport, Minister for Roads, Minister for the Arts, Minister for Music and the Night-time Economy, Minister for Jobs and Tourism  [Day] [Month] 2025 |