Schedule

THRIVE AND DANDENONG EMPLOYMENT HUBS

FEDERATION FUNDING AGREEMENT – Affordable Housing, Community Services and Other

| 16BTable 1: Formalities and operation of schedule |  |
| --- | --- |
| 17BParties | 18BCommonwealth 19BVictoria |
| 20BDuration | 21BThis Schedule is expected to expire on 30 June 2029 or on completion of projects, including final performance reporting and processing of final payments against milestones. |
| 22BPurpose | 23BThis Schedule will support the delivery of two different time-limited employment hub services within Victoria. 24BTwo hub service agreements, with different delivery partners, will be entered into with the Victorian Government. - 25BThe Victorian government will enter into an agreement for $2.0 million with the Brotherhood of St Laurence (BSL) to deliver Thrive Hubs in Broadmeadows and Frankston through to 30 June 2027. 26BThe Thrive Hubs are community-based, person-centered services that provide a range of services to enhance an individual’s capacity for employment or further education. - 27BThe Victorian government will enter into an agreement for $1.5 million with the Greater Dandenong City Council (GDCC) (or one of its respective entities) for the establishment and delivery of a Dandenong Employment Hub to operate until 30 June 2029. 28BThe Dandenong Employment Hub will be a ‘bricks and mortar’ hub that improves accessibility and joins up services across the employment and related services ecosystem. The aim of the Hub is to increase employment and economic participation of people in the region including the large and diverse Culturally and Linguistically Diverse (CALD) population, and those with other barriers to economic participation. |
| 29BEstimated financial contributions | The Commonwealth will provide an estimated total financial contribution to Victoria of $2.5 million in respect of this Schedule. Table 1 ($ million); 2025-26; 2026-27; 2027-28; Total. Estimated total budget; 1.85; 1.50; 0.15; 3.50. Less estimated National Partnership Payments; 1.35 1.00; 0.15; 2.50. Thrive Hubs; 0.75; 0.25; 0.00; 1.00. Dandenong; 0.60; 0.75; 0.15; 1.50. Balance of non-Commonwealth contributions. Thrive Hubs; 0.50; 0.50; 0.00; 1.00. Note: The Victorian Government will contribute $1.0 million towards Thrive Hubs. |
| 30BAdditional terms | The Commonwealth and the Victorian Government commit to ongoing regular communication to support the administration of the agreements and support the collaborative and efficient delivery of this Schedule. Regular meetings will occur over the life of the Schedule. The first 12 months will see at a minimum, monthly meetings and then move to at least quarterly meetings. A jointly developed Joint Implementation plan (JIP) will outline and be the overarching guide to delivery and governance of the two hub initiatives. The JIP will be a living document and can be amended, through mutual agreement by senior departmental officials of the Commonwealth and Victoria. The Victorian government will enter into service agreements with the respective parties. The agreement terms will include a requirement that information provided to the Victorian Government by the hub service partner can be subsequently shared with the Commonwealth. The Victorian government will provide copies of the hub service partners’ Project Status Report (or similar reports as detailed within the agreements) to fulfil the milestone requirements, as outlined in Table 2. These will document the progress of the hub service, including progress toward the achievement of their outcomes. The Commonwealth will maintain an active role in ongoing governance and consideration of data and project outcomes throughout the delivery of both Hub services. - In respect of the Dandenong Hub and its establishment phase, the Commonwealth will actively support and provide project management assistance and collaborate on community consultation and stakeholder activities with the hub service partner. |

| 31BTable 2: Performance requirements, reporting and payment summary |  |  |  |
| --- | --- | --- | --- |
| 32BOutput | 33BPerformance milestones | 34BReport due | 35BPayment |
| 0BDelivery of the Thrive and Dandenong Employment Hubs in Victoria. | Agreement by the Commonwealth and Victoria senior department officials to the Joint Implementation plan. | 1B30 September 2025 | 2B$1.05m |
|  | 3BContracts between the Victorian Government and Brotherhood of St Laurence (BSL) and Greater Dandenong City Council (GDCC) are executed and full copies provided to the Commonwealth. | 4B31 December 2025 | 5B$0.30m |
|  | Commonwealth acceptance of BSL and GDCC Project Status Reports and expenditure reporting as documented in the funding agreement with the Victorian Government for the period 1 October 2025 – 31 July 2026. | 6B31 August 2026 | 7B$0.50m |
|  | Commonwealth acceptance of BSL and GDCC Project Status Reports and expenditure reporting as documented in the funding agreement with the Victorian Government for the period 1 August 2026 – 28 February 2027. | 8B31 March 2027 | 9B$0.50m |
|  | Commonwealth acceptance of a GDCC Project Status Report and expenditure reporting as documented in the funding agreement with the Victorian Government for the period 1 March 2027 – 29 February 2028. | 10B31 March 2028 | 11B$0.15m |
|  | Commonwealth acceptance of BSL Final Report, including evaluation material, and Financial Acquittal Report. | 12B30 October 2027 | 13BNil |
|  | Commonwealth acceptance of the GDCC Final Report, including evaluation material, and Financial Acquittal Report. | 14B30 September 2029 | 15BNil |

| The Parties have confirmed their commitment to this schedule as follows: |  |  |
| --- | --- | --- |
| Signed for and on behalf of the Commonwealth of Australia by The Honourable Amanda Rishworth MP Minister for Employment and Workplace Relations [Day] [Month] 2025 |  | Signed for and on behalf of the State of Victoria by The Honourable Natalie Suleyman MP Minister for Veterans Minister for Small Business and Employment Minister for Youth [Day] [Month] 2025 |