# Thriving Kids

National Agreement on Foundational Supports – bilateral agreement

# Part 1 - Formalities and Operation of Bilateral Agreement

## Parties to the Agreement

- The Agreement is between the Commonwealth and New South Wales.

## Duration

- This Agreement:

  - will expire on 30 June 2031 unless terminated by agreement in writing by the Parties or replaced by a new agreement

  - may be amended by agreement in writing by the Parties.

## Purpose

- This Agreement is a Schedule to the National Agreement on Foundational Supports and should be read in conjunction with that Agreement and the Heads of Agreement on the National Health Reform Agreement, National Disability Insurance Scheme reforms and Foundational Supports (Heads of Agreement).

- In the event of divergence between:

  - this Agreement and the Heads of Agreement, the Heads of Agreement prevails

  - this Agreement and the National Agreement on Foundational Supports, the National Agreement on Foundational Supports prevails.

- This Agreement will support the delivery within New South Wales of services, supports and information for children aged 8 years and under with developmental delay and/or autism with low to moderate support needs, and their families, carers, and kin. These services, supports and information are collectively known as Thriving Kids.

- Supports delivered under this Agreement must align with the National Model: Thriving Kids and Commonwealth and State Delivery Responsibilities for Thriving Kids, outlined in Schedules B and C of the National Agreement on Foundational Supports, with appropriate local adaptation to the specific needs and circumstances of New South Wales.

- This Agreement establishes a framework for cooperative design and consideration of Thriving Kids supports:

  - the Commonwealth retains full discretion to approve/request amendment/decline an Implementation Plan. Approval of an Implementation Plan is a precondition to any Commonwealth financial contribution

  - nothing in this Agreement creates a binding obligation on the Commonwealth to fund services unless and until New South Wales Implementation Plan is approved and funding made available through appropriation.

## Estimated financial contributions

- The Commonwealth, states and territories will co-fund Thriving Kids at a cost of up to $4 billion new investment over 5 years (capped for all parties, split 50:50 on a per capita basis 0-64 years). All servicing/program costs, administration/overhead costs, indexation and demand management strategies required under Thriving Kids services are to be covered within this $4 billion cap, with the volume of services aligned to this envelope.

- The Commonwealth will provide a capped financial contribution to New South Wales totalling $442.4 million (over 5 financial years: 1 July 2026 to 30 June 2031), towards Thriving Kids as outlined in Schedule A - Financial Contributions:

  - the Commonwealth financial contribution will be allocated in accordance with the funding methodology outlined at Schedule A - Financial Contributions and paid in accordance with Table 1.

- The Commonwealth will use its residual financial contribution of up to $600 million over 5 years, for activities and services aligned with Schedule C of the National Agreement on Foundational Supports and Schedule B - Service Delivery of this Agreement.

- New South Wales will deliver a final Implementation Plan that is acceptable to the Commonwealth, as a condition of receiving Commonwealth funding and must meet its matched funding contribution over the period of this Agreement based on Schedule A - Financial Contributions.

- The Commonwealth will also provide its final Implementation Plan to New South Wales as part of its obligations under this Agreement.

- Financial contributions must only be used in the provision of Thriving Kids in-scope activities specified in Schedule B and C of the National Agreement on Foundational Supports and Schedule B - Service Delivery of this Agreement.

- The Parties funding contributions must be aligned with the additionality principle outlined in Schedule A - Financial Contributions and as per clauses 60 and 61 in National Agreement on Foundational Supports.

- Evidence of implementation of Thriving Kids supports and adherence to the additionality requirements will be required through statements of claims by the responsible Minister as per Table 1. This is a reciprocal requirement on all Parties.

- Activities delivered under this Agreement are to be managed within the agreed funding envelope and are not demand-driven entitlements. New South Wales is responsible for managing service volume, prioritisation and delivery settings to operate within available funding.

- Parties agree that the total Commonwealth and New South Wales funding contribution is to be spent within the term of this Agreement, with all funding to be fully expended by 30 June 2031. Unspent Commonwealth funding contributions to New South Wales not fully expended by 30 June 2031 will be returned to the Commonwealth.

- In the instance that this Agreement is terminated early, Parties agree that any unspent Commonwealth funding contributions to New South Wales will be returned to the Commonwealth.

# Part 2 - Governance

- Consistent with the National Agreement on Foundational Supports, the Parties will work collaboratively through established governance mechanisms and mutually agree any additional governance mechanisms as required to monitor performance under this Agreement and to respond to any emerging issues as required.

- Clause 8(c) of the Heads of Agreement and Part 3 of the National Agreement on Foundational Supports delegates governance arrangements for this Agreement to responsible Ministers in each jurisdiction.

- In the Commonwealth, the Minister for Health and Ageing, Minister for Disability and the NDIS is the responsible Minister for the purposes of this Agreement.

- In New South Wales, the Minister for Minister for Disability Inclusion is the responsible Minister for the purposes of this Agreement.

- Responsible Ministers can authorise agreed functions of this Agreement to Senior Officials as required.

- Dispute resolution for this Agreement has been set out in clauses 44 to 47 of the National Agreement on Foundational Supports.

- Amendments to this Agreement will only be made with agreement of the Parties in writing. All proposed amendments must be mutually agreed upon to ensure the continuity of this Agreement and its associated funding arrangements.

# Part 3 - Principles

- The combined New South Wales and Commonwealth investment will be used to deliver information, services, supports and critical enablers as outlined in the National Model: Thriving Kids in Schedule B of the National Agreement on Foundational Supports.

- Supports delivered under this Agreement will be delivered within a capped funding envelope with Parties putting systems in place to monitor and manage demand through proactive approaches that operate to ensure community expectations are being met.

- Supports will be designed and implemented to ensure affordability for service users.

- Supports delivered under this Agreement will be designed to respond to the different developmental needs within the Thriving Kids cohort (ages, developmental delay, autism, intersectional considerations).

- Supports will be delivered in all settings families and children already interact with (where children live, learn, play) – including but not limited to Early Childhood Education and Care and school settings – with the type and mode of support/s provided based on the child and family’s needs.

  - the extent to which particular settings are used as a site for delivery will take into account capped funding considerations.

- The Parties agree children do not require a diagnosis to access Thriving Kids and any assessment of need will be based on functional need and implemented in a way that supports early access to services appropriate to individual needs.

- Children aged 8 and under with developmental delay and/or autism with low to moderate support needs will not be eligible for the NDIS from 1 January 2028 and will be supported by Thriving Kids.

  - a child who accesses Thriving Kids may concurrently be eligible for the NDIS, subject to the usual NDIS arrangements, where they also have substantially reduced functional capacity (high support needs).

- All services have feedback loops to ensure continuous improvement and escalation pathways for complaints.

- The Parties will support the interface between mainstream services, Thriving Kids and the NDIS, consistent with clause 21(i) of the National Agreement on Foundational Supports:

  - the Commonwealth will provide for consultation the definition of low to moderate support needs to New South Wales in accordance with clause 14(a) of the Heads of Agreement to support all states and territories to apply nationally consistent functional needs identification and triage arrangements for Targeted Supports, consistent with National Model: Thriving Kids:

    - Commonwealth consultation with states and territories around definitions and the translation of these definitions into functional needs identification and triage arrangements for Targeted Supports will commence by no later than 18 May 2026

    - the requirement to apply a nationally consistent approach will not require all states and territories to use a single common needs identification tool

    - New South Wales will provide information to the Commonwealth about its approach to functional needs identification and triage prior to 1 October 2026.

- Programs and services linked to Thriving Kids investments must be visible and identifiable to service users and the wider community through navigation and referral services and resources and through the use of national branding. This does not limit the continued use by the Parties of existing programs and service names delivered by the Parties.

- Parties agree to work collaboratively with all stakeholders, including but not limited to, early childhood, health, education, disability and community service in the development and implementation of services.

# Part 4 - Roles and Responsibilities

- The Commonwealth will commence rollout of supports no later than 1 October 2026, in consultation with New South Wales to ensure effective connection with existing and proposed systems with specific rollout arrangements to be set out in the Commonwealth Implementation Plan.

- New South Wales will commence rollout of supports no later than 1 October 2026, in consultation with the Commonwealth to ensure effective connection with existing and proposed systems with specific rollout arrangements to be set out in the New South Wales Implementation Plan as agreed by the Parties.

- All supports are to be fully scaled and in place by 1 January 2028.

- Parties agree to deliver this Agreement in line with nationally consistent system parameters in clauses 21 - 23 of the National Agreement on Foundational Supports.

- Consistent with clauses 21 - 23 of the National Agreement on Foundational Supports, Parties agree to:

- participate in oversight and governance arrangements for Thriving Kids, including contributing to joint decision making on implementation planning where New South Wales and Commonwealth services delivered as part of this Agreement intersect

- collaboratively monitor performance

- collaboratively identify, escalate and manage risks or issues that may affect the delivery of Thriving Kids including, but not limited, to timely and effective:

- delivery of activities, outputs and services

- management of issues or concerns raised by service users

- management of issues affecting reporting, data collection or evaluation requirements.

- avoid creating service gaps between mainstream services, Thriving Kids and the NDIS, while ensuring additional Thriving Kid services do not exceed agreed funding caps.

- work collaboratively to support consistent and clear communication to the public on intent, implementation and outcomes of Thriving Kids. This includes collaboration around a national communications campaign delivered by the Commonwealth and key New South Wales-level communications.

- collaborate on workforce, market and system stewardship in alignment with clause 21(g) of the National Agreement on Foundational Supports.

- Parties will share information between each other and key workforces on services funded under Thriving Kids, and how to access them including any additions or changes, in a timely manner, to support national and local service navigation offerings.

- consider the findings, recommendations, and/or outcomes of the rapid independent Review commissioned consistent with clause 37 of the National Agreement on Foundational Supports.

# Part 5 - Service Delivery

- The Parties agree to deliver the services and activities, aligned with:

  - the National Model: Thriving Kids, including the domains of support, enablers and service principles outlined in Schedule B of the National Agreement on Foundational Supports

  - quality and safety parameters as per clauses 21 and 22 of the National Agreement on Foundational Supports and system parameters outlined in clause 21 of the National Agreement on Foundational Supports, including delivery approaches that are flexible and tailored to enable access for people living in remote and regional areas and in thin markets

  - Commonwealth and state delivery responsibilities in Schedule C of the National Agreement on Foundational Supports

  - the detail in the agreed Implementation Plan

  - additionality requirements as outlined in clauses 60 and 61 of the National Agreement on Foundational Supports.

- New South Wales agrees to deliver services and activities as per Schedule B – Service Delivery to this Agreement. The Commonwealth agrees to deliver services and activities as per Schedule B – Service Delivery to this Agreement. An overview of delivery roles, services and the profile of investments for New South Wales and the Commonwealth is to be included as part of Schedule B – Service Delivery to this Agreement and the Parties Implementation Plans.

- In line with Schedule C of the National Agreement on Foundational Supports, the Commonwealth continues to investigate the delivery of:

- a national MBS 3-year-old health and development check to complement state child development assessments and checks to support early identification of children with developmental delay/neurodevelopmental difference

- integration of state child health checks into national online/digital information system/record to support early identification of children with developmental delay/neurodevelopmental difference.

- New South Wales and the Commonwealth must each make a public statement or publish a factsheet, by no later than 31 March 2026 that outlines how they intend to finalise service design and engagement/consultation with stakeholders, ahead of finalisation of the Implementation Plan by 31 May 2026.

# Part 6 - Implementation Plans

- New South Wales will, in consultation with the Commonwealth, complete and maintain an Implementation Plan that details critical New South Wales implementation information and references relevant Commonwealth implementation information. The Implementation Plan template will be agreed by the Commonwealth and New South Wales.

- The Commonwealth will, in consultation with States and Territories, complete and maintain a Commonwealth Implementation Plan for national supports:

- as part of this Implementation Plan, the Commonwealth will confirm whether services outlined in Schedule B of this Agreement will be delivered as national supports.

- The Implementation Plans will be consistent with the services, outputs, milestones and timeframes set out in this Agreement. At a minimum the Implementation Plans must cover:

- the expected total costs of services to be delivered each financial year, and over the life of the Agreement, in accordance with additionality requirements in clauses 60 and 61 of the National Agreement on Foundational Supports

- the expected profile of costs against the domains of support specified in the National Model: Thriving Kids outlined in Schedule B of the National Agreement on Foundational Supports

- the servicing arrangements of the funded activity, including the settings, reach, coverage and make-up of the supports and services

- the specific cohort/s expected to benefit from funded services and supports, including services that consider the unique needs of cohorts such as First Nations, culturally and linguistically diverse groups, children in out-of-home care, intersectional needs and families experiencing crisis or family and domestic violence, and services in rural and remote and thin markets

- the interface arrangements with other relevant service systems, including referral, consent, privacy and information sharing

- alignment with the national model domains of support, enablers and service principles as per Schedule B of the National Agreement on Foundational Supports.

- The Parties agree to share the draft Implementation Plan content with each other for review and feedback.

- Parties agree their Implementation Plans will be completed by 31 May 2026.

- Parties agree to provide evidence of commencement, and full implementation, of Thriving Kids supports, with reference to the Implementation Plan, through a statement of claims by the responsible Minister.

- Where New South Wales is unable to maintain, deliver or report against the agreed Implementation Plan, New South Wales will work collaboratively with Commonwealth to identify contributing factors and agree on appropriate remedial actions as per clause 55 of the National Agreement on Foundational Supports.

- The Parties may vary the Implementation Plans. A variation must:

  - be in writing

  - clearly identify the provisions of the Implementation Plan being amended; and

  - be signed by authorised representatives of each Party.

- A variation agreed under this clause does not constitute a variation to this Agreement.

# Part 7 - Reporting, Monitoring and Evaluation

- Existing reporting requirements for all Parties will remain in place where the service is existing or expanded, consistent with clause 17(e) of the Heads of Agreement.

- Reporting obligations in this Agreement apply to all Parties and should provide information necessary to support the Parties in delivering on the objectives of this Agreement.

- Information referred to in Part 7 will not be published without the consent of New South Wales.

- New requirements must be agreed by the Parties and will only be applied to the extent necessary to provide clarity on Thriving Kids funding; children and families supported, method and intensity of support, outcome measurement, evaluation and continued learning to realise and sustain the intent, outcomes as listed in this Agreement, the Implementation Plans and the principles of Thriving Kids outlined in Schedule B of the National Agreement on Foundational Supports, consistent with clause 17(e) of the Heads of Agreement.

- Data and information will be provided:

- in Implementation Reports, consistent with clause 30(d) of the National Agreement on Foundational Supports, with agreed elements included in the Annual Public Report

- as part of evaluation activities and the rapid independent Review to assess implementation progress outlined in clause 37 - 41 of the National Agreement on Foundational Supports.

- Data and information collected under this Agreement remains the responsibility of the collecting Party but will be shared with the Commonwealth for the purposes of monitoring, evaluation, policy development and public reporting:

- the Commonwealth may use de-identified data to undertake national analysis, data linkage and evaluation activities, including through authorised third-party agencies, consistent with the relevant privacy legislation

- publications drawing on shared data will acknowledge contributions of all parties and be subject to consultation, but consent will not be unreasonably withheld where material is de-identified and relates to national performance.

- Parties agree to collect to the best of their abilities and supply agreed data and information for the purposes indicated in clause 59 of this Agreement. Agreed data and information will be provided in the following domains:

- details of investments – service types, settings and geographical coverage and expenditure

- number of clients supported and totals by each program/service/initiative

- duration and frequency of support provided

- average time between referral/intake and receipt of support

- client outcomes

- demographics and intersections – age, gender, First Nations, CALD

- feedback, complaint and complaint resolution trends.

- Parties agree to provide timely access to agreed datasets necessary to assess outcomes. The specificity of data will depend on the type of program or service, with these details to be agreed in the Evaluation and Reporting Framework.

- Reported information will be shared reciprocally between both Parties, consistent with the timeframes outlined in clause 30(d) of the National Agreement on Foundational Support and Table 1 of this Agreement.

- Parties agree to work collaboratively to design, agree and implement an Evaluation and Reporting Framework consistent with clause 30(f) of the National Agreement on Foundational Supports, this will include data reporting requirements and templates. The Evaluation and Reporting Framework will be agreed in writing.

- The Evaluation and Reporting Framework will support the provision of both national and jurisdiction level information that contributes to an effective evaluation of Thriving Kids.

- Evaluation and reporting arrangements must commence as soon as practicable after 1 October 2026, aligned with the phased rollout and scaling within New South Wales and the agreed Evaluation and Reporting Framework.

- The scope of the Evaluation and Reporting Framework will align with the domains as per clause 61 of this Agreement and may also include information on:

- safeguards

- service integration and interoperability

- research and evaluation questions.

- Parties agree to seek consent of participants to facilitate any client surveys or other methodologies that may be utilised as part of agreed arrangements.

Table 1: Performance requirements, reporting and payment summary

| OUTPUT | REQUIREMENT | DUE DATE | PAYMENT |
| --- | --- | --- | --- |
| Milestone 1 | Public statement to be made, or a factsheet published, that outlines how New South Wales and the Commonwealth each intend to finalise service design, including any engagement/consultation with stakeholders, ahead of finalisation of the Implementation Plan by 31 May 2026 | 31 March 2026 |  |
| Milestone 2 | New South Wales and the Commonwealth to share draft Implementation Plans for review and feedback | 1 May 2026 |  |
| Milestone 3 | Commonwealth acceptance of the New South Wales Implementation Plan | 31 May 2026 |  |
| Milestone 4 | New South Wales and the Commonwealth agree data and information requirements as part of the Evaluation and Reporting Framework outlined in Part 7 of this Agreement, and as defined below Table 1 | 30 June 2026 |  |
| Payment year 1 - 2026/27 | Payment is dependent of satisfactory completion of milestones 1, 2, 3 and 4 | July 2026 | $88.5m |
| Milestone 5 | ## New South Wales and Commonwealth commence initial rollout of its contribution to Thriving Kids. New South Wales and Commonwealth provide evidence of implementation of Thriving Kids supports, and adherence to the additionality requirement specified in the estimated financial contributions section of this Agreement, through a statement of claims by the responsible Minister | No later than 1 October 2026 |  |
| Milestone 6 | Commonwealth acceptance of the 6 monthly Implementation Report, as outlined in clause 30(d) of the National Agreement on Foundational Supports and consistent with Part 6 and Part 7 of this Agreement, provided by New South Wales | April 2027 |  |
| Milestone 7 | Commonwealth acceptance of the 6 monthly Implementation Report, as outlined in clause 30(d) of the National Agreement on Foundational Supports and consistent with Part 6 and Part 7 of this Agreement, provided by New South Wales | September 2027 |  |
| Milestone 8 | Annual Public Report published | December 2027 |  |
| Payment year 2 - 2027/28 | Payment is dependent on satisfactory completion of milestones 5, 6 and 7 | October 2027 | $88.5m |
| Milestone 9 | New South Wales and Commonwealth supports are fully scaled and in place. New South Wales and the Commonwealth provide evidence of full implementation of Thriving Kids supports and adherence to the additionality requirement specified in the estimated financial contributions section of this Agreement through a statement of claims by the responsible Minister | 1 January 2028 |  |
| Milestone 10 | Commonwealth acceptance of the Annual Implementation Report, as outlined in clause 30(d) of the National Agreement on Foundational Supports and consistent with Part 6 and Part 7 of this Agreement, provided by New South Wales | September 2028 |  |
| Milestone 11 | Annual Public Report published | December 2028 |  |
| Payment year 3 - 2028/29 | Payment is dependent on satisfactory completion of milestones 9 and 10 | October 2028 | $88.5m |
| Milestone 12 | Supports remain scaled and in place |  |  |
| Milestone 13 | Draft terms of reference for the rapid independent Review agreed for subsequent consideration by First Ministers | January 2029 |  |
| Milestone 14 | Commonwealth acceptance of the Annual Implementation Report, as outlined in clause 30(d) of the National Agreement on Foundational Supports and consistent with Part 6 and Part 7 of this Agreement, provided by New South Wales | September 2029 |  |
| Milestone 15 | Annual Public Report published | December 2029 |  |
| Payment year 4 - 2029/30 | Payment is dependent on satisfactory completion of milestones 12, 13 and 14 | October 2029 | $88.5m |
| Milestone 16 | Supports remain scaled and in place |  |  |
| Milestone 17 | Commonwealth acceptance of the Annual Implementation Report, as outlined in clause 30(d) of the National Agreement on Foundational Supports and consistent with Part 6 and Part 7 of this Agreement, provided by New South Wales | September 2030 |  |
| Milestone 18 | Annual Public Report published | December 2030 |  |
| Payment year 5 – 2030/31 | Payment is dependent on satisfactory completion of milestone 16 and 17 | October 2030 | $88.5m |
| Milestone 19 | Supports remain scaled and in place |  |  |
| Milestone 20 | New South Wales acquittal of the 5 years of joint investment, showing Commonwealth and State funding as per clause 17 of this Agreement. The Commonwealth will also acquit its investment over the 5 years | August 2031 |  |
| Milestone 21 | Commonwealth acceptance of the Annual Implementation Report, as outlined in clause 30(d) of the National Agreement on Foundational Supports and consistent with Part 6 and Part 7 of this Agreement, provided by New South Wales | September 2031 |  |
| Milestone 22 | Annual Public Report published | December 2031 |  |

As outlined in Part 6 of this Agreement, the Implementation Plan outlines how the jurisdiction (and Commonwealth at a national level) will roll out Thriving Kids. Its focus is on program level information and will include, but not be limited to, details on: scaling of services; quality, safety and safeguarding measures; and alignment with the national model and delivery responsibilities outlined in Schedule B and Schedule C of the National Agreement on Foundational Supports. The Implementation Plan can be updated when required via joint agreement. An Implementation Plan report will be provided at 6-month mark (April 2027) as per clause 30(d) of the National Agreement on Foundational Supports to meet milestone 6.

Annual Implementation Report: a reporting template will be agreed as per milestone 4. The template will be used to produce an Annual Implementation Report by jurisdictions and the Commonwealth against the Implementation Plan and will include program and service user level data, on Thriving Kids. (As per clause 30(d) of National Agreement on Foundational Supports).

Annual Public Report (as per clause 30(e) of the National Agreement on Foundational Supports): developed from jurisdictions and Commonwealth’s Annual Implementation reporting. Commonwealth to develop the report with agreed input by jurisdictions.

The Evaluation and Reporting Framework will outline the approach to data collection, evaluation and the rapid independent Review. This may include components such as methodology, data sources, outcome measures, stakeholders and timing.

The Parties have confirmed their commitment to this Thriving Kids Bilateral Agreement as follows:

| Signed for and on behalf of the Commonwealth of Australia by The Honourable Mark Butler MP Minister for Health and Ageing Minister for Disability and the National Disability Insurance Scheme 2 March 2026 |  | Signed for and on behalf of the State of New South Wales by The Honourable Kate Washington MP Minister for Families and Communities and Minister for Disability Inclusion 6 March 2026 |
| --- | --- | --- |

# Schedule A – Financial Contributions

This Schedule is to be read in connection with the estimated financial contributions section of this Agreement.

## Summary

New South Wales will invest a total of $1,074.3 million in their jurisdiction, over 5 years (2026-27 to 2030-31), aligned to Schedule B and C of the National Agreement on Foundational Supports and other parameters in this Agreement. This comprises:

- a New South Wales contribution of $631.9 million, and

- the Commonwealth’s contribution to New South Wales of $442.4 million.

| ($ million) | [2026-27] | [2027-28] | [2028-29] | [2029-30] | [2030-31] | Total* |
| --- | --- | --- | --- | --- | --- | --- |
| Commonwealth contribution to New South Wales | 88.5 | 88.5 | 88.5 | 88.5 | 88.5 | 442.4 |

*Sum of contributions will not add to the sub-total due to rounding

Expenditure of New South Wales contribution is to commence from 2026-27 financial year, with phasing to be detailed in the New South Wales Implementation Plan developed by 31 May 2026 in accordance with Part 6 of this Agreement.

The Commonwealth will also invest its residual contribution of up to $600 million, over 5 years (2026-27 to 2030-31), commencing in 2026-27, on national initiatives under Thriving Kids aligned to Schedule B and C of the National Agreement on Foundational Supports and other parameters in this Agreement. Phasing of this investment is to be detailed in the Commonwealth Implementation Plan developed by 31 May 2026 in accordance with Part 6 of this Agreement.

## Funding allocation

- The $4 billion for Thriving Kids will cover five financial years 2026-27 to 2030-31.

- The Commonwealth’s contribution is comprised of the delivery of Commonwealth services of up to $600 million with remaining funding of at least $1.4 billion to be provided to states and territories in accordance with the terms specified in the funding allocation section.

- Funding will be distributed on a per capita basis, with state population shares to be taken from the of ages 0-64 years. State population shares will be taken from the December data from the year that the Census was undertaken (that is, December 2021).

- The calculation of New South Wales matched contribution will be the total over the five years of the Agreement.

## Additionality Assessment

- An assessment by New South Wales and the Commonwealth must be undertaken to provide assurances to all Parties that their contribution to Thriving Kids funding is additional to existing servicing effort and funding as per clause 17 of the Heads of Agreement.

- The additionality assessment must include a baseline of associated expenditure for services that meet the description and intent of Thriving Kids services, as outlined in Schedule C of the National Agreement on Foundational Supports, and existed in New South Wales in the financial year 2022-2023.

- Additionality will be assessed at the aggregate level of existing investment across all relevant programs combined, rather than for each program individually.

- Parties agree to inform each other of any proposed major changes to the baseline during the life of the Agreement in good faith, and on the understanding that there should not be any reduction of funding to the baseline.

# Thriving Kids Bilateral Agreement Schedule B: Service Delivery

This Schedule provides an overview of the additional services that will be delivered by the Parties, consistent with Part 5 of this Agreement, and aligned to Schedule B and C of the National Agreement on Foundational Supports.

Note:

- The final design and scope of individual services and initiatives will be refined by the Parties as part of implementation planning activities.

- All indicative expenditure to be further refined by the Parties ahead of commencement of services.

| National Model component |  | State-led services | Indicative expenditure range over 2026-27 to 2030-31) as a percentage of New South Wales total expenditure | Commonwealth-led national initiatives* | Indicative expenditure range over 2026-27 to 2030-31) as a percentage of Commonwealth’s total expenditure |
| --- | --- | --- | --- | --- | --- |
| Improved awareness of developmental delay/neurodevelopmental difference | # Activities that support greater parent/family/kin awareness of childhood development and neurodevelopmental difference (including autism) to support early identification where a child may be developing differently to their peers. | # State based supports for improved awareness - NSW will assist in promoting the Commonwealth’s awareness activities. - NSW will deliver promotional activities to raise awareness of available services and resources and how they can assist families with their child’s development. | # Existing service, or cost captured in enablers | # National Communications activities # A communications campaign and/or other activities will work to: # raise parental/family awareness around the signs of developmental delay/neurodevelopmental difference # build understanding of new service pathways and services available to support families and professionals # this will include a specific support for direct engagement with the Autistic and autism community. # This will complement any state awareness raising activities. | # 5% |
| Early identification of children with developmental delay/neurodevelopmental difference | # Routine child development and health assessments or checks. | # Early identification of children with developmental delay/neurodevelopmental difference - NSW has made significant investments in early identification of developmental needs, particularly through our child health and development check programs. This includes the recent addition of 4-year-old health and development checks delivered within early childhood education and care settings, further strengthening our approach to identifying and supporting children’s needs early. NSW provides child health and development checks through Aboriginal Medical Services, child and family health services, early childhood education and care services, complementing investment in foundational supports. Existing investment in these services will not be captured as part of NSW's financial commitment to Thriving Kids. - NSW will ensure all its Thriving Kids services support early identification by providing families with information and guidance on the types of health and development checks, services and supports available, and pathways to further supports if required. | # Existing service, or cost captured in enablers and best practice parenting supports | # Identification Comprehensive Health Assessment Program (CHAP) # Adapt the CHAP to offer annual health assessments for children aged 3-12 years with established or suspected neurodevelopmental delays or autism. The adapted CHAP would support children identified as having possible neurodevelopmental delays and/or autism to receive ongoing, coordinated, primary health care and other necessary supports, including appropriate referrals to Thriving Kids supports. | # 20-30%* |
| Information, advice and navigation | # National and local digital/phone-based information and advice on childhood development and Autism; and navigation support on where and how to access relevant supports. # Information on available Thriving Kids supports that is maintained by all jurisdictions on an ongoing basis and is readily accessible to the community and key workforces who interact with or may refer children for supports. | # State based information, advice, navigation and/ or intake - NSW will publish and maintain a website with statewide information about available services as well as resources to support families, workforce, and service providers. - NSW will provide a statewide information and referral helpline to assist families to access the services they need. - NSW will deliver sector engagement activities and communities of practice to support local coordination of services, information and referrals. - Commissioned services will be easily accessible and present a low barrier to entry for families seeking support and information. | # Cost captured in enablers and best practice parenting supports | # Online and phone information and advice, navigation, tools and resources # National online information portal and self-service finder # Funding of a national provider who is known as a trusted source of online parenting advice and disability advice. Would provide information, tools and resources on development (things family can do at home to build child’s skill). Materials are evidence based/peer reviewed. They would also deliver a national online self-service finder (for all Thriving Kids supports, including state-based offerings). # National phone information, advice and service finding # Information on developmental delay and autism for parents/family and advice on things families can do to support their child’s development. They may also offer secondary advice for key professionals around development. # Staffed by professionals (child and maternal health nurses, allied health). # Referral/connection to state-based intake/navigation offerings. # Autism-specific national phone advice and service finding for families of Autistic children # Funding a national provider who is trusted to provide tailored information and support for families, particularly associated with transitions and engaging with new and unfamiliar environments, and what a diagnosis may mean. # Staffed by experts with practice advice and lived experience best placed to support this cohort. # Referral/connection to state-based intake/navigation offerings | # 32-35% |
| Best practice parenting supports and programs | # Programs and/or supports to empower families, carers and kin with resources and skills required to assist and improve their child’s learning and development through everyday activities. There is a soft entry to these supports/programs for the eligible cohort. | # Best practice parenting supports and programs # NSW will commission additional supported playgroups, providing structured, evidence-based gatherings for children aged 0-5 and their caregivers that foster support through facilitated play and community engagement. # NSW will facilitate in-reach by allied health professionals to supported playgroups, enabling practitioners to participate directly in sessions where they can provide advice and/or screen for developmental needs. # NSW will commission new peer support and parenting programs, equipping families with new skills and strategies to support their child’s development. | # Up to 20-30% of final funding envelope | # Best practice parenting supports # Positive Partnerships Program (augmentation) # Free professional learning for teachers and other school staff and workshops and information sessions for parents and carers to help build knowledge, skills and awareness of autism. # Funding will complement existing Commonwealth investment to improve outreach to underserved cohorts # Virtual peer support for Autistic children # Online peer support for children with autism and their families and kin, to assist with transitions at key points like entering childcare, preschool or school. # Mental Health in Primary Schools (MHiPS) # A central hub to enable engagement across jurisdictions, data collection, consistency in program roll out and early intervention mental health needs of children in regional, rural and remote schools. State governments would continue funding wellbeing coordinators in jurisdictions this operates. | # <5% |
| Targeted supports | # Targeted supports including group and 1:1 allied health, low-cost assistive technology related to development; and more intensive capacity building to support families with complex needs/circumstances. # Access to targeted supports is based on nationally consistent functional needs identification and triage arrangements. # Support should be provided in all settings where children live, learn and play. | # Targeted Supports # NSW will commission, and in some contexts government may directly deliver, goal-based allied health group and 1:1 supports. In some circumstances, this will include provision of low-cost assistive technology when it is required to achieve therapy goals. Eligible children will access therapies in a range of settings. # Services will provide case coordination and family capacity building to support families to implement the strategies from allied health sessions, and to better understand and respond to their child’s needs. # NSW will administer access and demand management functions, including consistent functional needs assessment, to ensure targeted supports are used efficiently within the limited available funding. | # Up to 60-70% of final funding envelope | # Targeted Supports # Not applicable | # 0% |
| Priority cohorts and delivery locations | # Services within these domains should be designed to consider the unique needs of cohorts such as First Nations, culturally and linguistically diverse groups, children in out-of-home care, intersectional needs and families experiencing crisis or family and domestic violence, and those who may not regularly interact with the broader service ecosystem as well as geographical considerations including rural and remote and thin markets. | # Cohorts: First Nations # NSW will deliver targeted procurement activities to support new and existing Aboriginal Community Controlled Organisations to expand their services to deliver programs aligned to the Thriving Kids model and principles. Rural and remote # NSW Thriving Kids will consider the needs of children and families, including geographical impacts of service availability, to inform implementation planning and approach to service rollout and scaling. # NSW will complement and leverage existing exemplar rural and remote models of effective care to support implementation planning Other cohorts # All service delivery will be guided by best practice principles, ensuring programs are evidence-based, culturally sensitive, and responsive to the diverse needs of families and communities across NSW. # The design of services will include consideration of the needs of First Nations children and families, culturally and linguistically diverse groups, and rural and remote communities. # Since funding is limited, some services will be prioritised for certain groups. # Everyday settings where children live, learn and play: Primary care # NSW currently delivers existing supports for children and families through Child and Family Health services. Existing investment in these services will not be captured as part of NSW's financial commitment to Thriving Kids. # While primary care services will not form part of NSW’s Thriving Kids offering, primary care has a natural interface with Thriving Kids such as supporting early identification, and access to information and referrals. Neighbourhood centres # Neighborhood centers are trusted community hubs, frequently accessed by children and their families. # Thriving Kids will leverage neighborhood centers by expanding and enhancing existing programs, such as embedding allied health professionals into supported playgroups. # New programs and services will also be delivered within neighborhood centers to increase accessibility and relevance for local communities. Community-based organisations # Existing community-based organisations will serve as key delivery partners for both best practice parenting supports and targeted supports under Thriving Kids. # These organisations, known for their inclusive and family-friendly environments, will provide accessible spaces where families can receive a spectrum of services from drop-in advice to structured, intensive supports. # Professionals from allied health and parenting support fields will be embedded within these organisations, fostering early identification of needs, immediate support, and ongoing guidance for families in natural, familiar settings. Home # Some service types, such as family capacity building, can be delivered directly in the home by some commissioned partners to better address the unique needs of each family. # Home-based delivery allows practitioners to work closely with families in their natural environment, supporting practical skill-building and tailored interventions. # This approach enhances accessibility for families who may face barriers attending external sites and ensures strategies are relevant to the family's daily routines and context. Early Childhood Education and Care # NSW currently delivers health and development checks in ECEC centres. # NSW will explore models of delivery to coordinate targeted allied health support to children accessing support through Thriving Kids who are attending ECEC services, with consideration to the national Best Practice Framework for Early Intervention. # Potential areas of focus include supporting the role of ECEC settings in the early identification of developmental needs, and supporting families to access information, support and referrals to other services. Schools # NSW will commission Thriving Kids services that, in some circumstances, will be able to leverage schools for delivery. | # Cost captured in enablers, best practice parenting supports and targeted supports | # Facilitation of state delivery in Early Childhood Education and Care (ECEC) settings To ensure state-delivered targeted supports are able to effectively connect with/be delivered in ECEC settings. Targeted ECEC providers across Australia will be supported to facilitate access to (state delivered) drop-in Thriving Kids supports at ECEC sites. This would be on top of supports available from the Inclusion Support Program. # Note workforce measures include support for First Nations. | # 15-17% |
| Enabling functions | # Supporting workforce capability readiness in key sectors, including primary care/health, early childhood education and care and schools. # Reporting and evaluation of Thriving Kids. Effective reporting and evaluation arrangements are recognised as essential to the operation of the National Model. | # Workforce # NSW will deliver a sector transition plan and activities to support commissioned services to scale up, attract and retain a quality workforce. # NSW will facilitate sector-building activities to provide opportunities for workers to learn and share knowledge with each other. # NSW will deliver training for the workforce to facilitate evidence-based supported playgroups and peer and parenting programs, and to meet program requirements such as data collection and reporting. # NSW commissioned JMI to undertake and deliver a report on Workforce and Stewardship for Foundational Supports in early 2025, with findings and recommendations covering the remit of state and Commonwealth governments. # NSW notes many of the initiatives are within the Commonwealth’s remit, including tertiary education and placement supports for critical allied health workforces, were identified in the Thriving Kids Advisory Group Report and NSW looks forward to working with the Commonwealth on these. # Reporting /Evaluation # NSW will establish data collection and reporting processes and systems to support monitoring and evaluation of services. # NSW will establish a mechanism to engage academic and practice experts to provide advice and support continuous improvement throughout the early implementation stages of the program. # Centralised function # NSW will provide a central function to manage the implementation of programs and services, including access and demand management functions. | # Up to 10-20% of final funding envelope | # Workforce - National measures to assist workforce and build capacity readiness in key sectors, including primary care, ECEC and schools. # Online and face to face training and resources, including a child development micro credential/e-learning suite, targeted and adapted to specific workforces (GPs/MACH nurses/ECEC and school educators, professionals) involved in development. # This will support professionals to understand developmental concepts and have safe conversations with parents where they have identified developmental delay or neuro-developmental difference and encouraging families to connect with Thriving Kids, where appropriate. It will also support teachers and ECEC workers’ knowledge and skills around supporting common developmental disabilities/conditions, referral pathways, working with other professionals, implementing reasonable adjustments and communicating with parents/carers. # Coaching and capacity building for ECEC # Strengthen the role of Inclusion Agencies (IAs) to support early childhood educators in eligible CCS approved services to apply adjustments recommended by Thriving Kids or other relevant professionals, within educators’ skill sets. Coaching would provide practical, tailored advice. # Primary care practice skills uplift and capability framework # For children with neurodevelopmental differences and/or autism and their families. This would guide training, guidance, tools and other resources to support primary care professionals to better identify and respond to the needs of these children. This also contributes to government commitments through the Autism and Intellectual Disability Roadmaps. # Workforce - promote and embed the National Best Practice Framework for Early Childhood Intervention # This will raise awareness around the framework and develop detailed guidance materials on how practitioners can implement the Framework in service settings to improve the quality of supports. # National First Nations specific offering # Funding to NACCHO for capacity and capability uplift of workforce. Note: state-specific investments are also expected for First Nations children and families. # Funding to SNAICC for improving the awareness of Thriving Kids in First Nations communities, including their interactions with mainstream services, and working with Thriving Kids providers on best practice for First Nations children. # Reporting /Evaluation # Deliver Thriving Kids monitoring, reporting and evaluation. Funding is for a third party to work with governments to design and undertake developmental evaluation, the scheduled rapid implementation Review specified in the National Agreement and implementation monitoring. | # 23-26% |

*To be read in conjunction with clause 44 of this Agreement