Schedule

Yellow crazy ant control -Wet Tropics of Queensland FEDERATION FUNDING AGREEMENT – Environment

| Table 1: Formalities and operation of schedule |  |
| --- | --- |
| Parties | Commonwealth Queensland |
| Duration | This Schedule is expected to expire on 30 June 2028. |
| Purpose | This Schedule will support the delivery of a program to control yellow crazy ant infestations (with the aim of eradication), in and adjacent to the Wet Tropics of Queensland World Heritage Area. |
| Estimated financial contributions | The Commonwealth will provide an estimated total financial contribution to Queensland of $18.0 million in respect of this Schedule. |
| Additional terms | Nil |

| Table 1: Financial contributions to the state |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ($) | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 |  | 2027-28 | Total |
| Estimated total budget | 6,000,000.00 | 6,000,000.00 | 6,000,000.00 | 6,000,000.00 | 6,000,000.00 |  | 6,000,000.00 | 36,000,000.00 |
| Less estimated National Partnership Payments | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 |  | 3,000,000.00 | 18,000,000.00 |
| Balance of non-Commonwealth contributions | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 |  | 3,000,000.00 | 18,000,000.00 |

| Table 2: Performance requirements, reporting and payment summary |  |  |  |
| --- | --- | --- | --- |
| Output | Performance milestones | Report due | Payment |
| Delivery of a program to control yellow crazy ants (with the aim of eradication) in and adjacent to the Wet Tropics of Queensland World Heritage Area. | Commonwealth acceptance of: - a four-year (2023 -2026) Project Plan for control of yellow crazy ants in the Wet Tropics. - a 2022-23 Annual Implementation Plan detailing project scope, project schedule, communication plan, high level design plans and a risk management plan. | 30/04/2023 | $3,000,000.00 (paid) |
|  | - Evidence that completion of scheduled stages/deliverables is in accordance with the agreed four-year Project Plan and the 2022-23 Annual Implementation Plan. - Commonwealth acceptance of: - reviewed and updated four-year Project Plan. - a 2023-24 Annual Implementation Plan detailing project scope, project schedule, communication plan, high level design plans and a risk management plan. | 25/08/2023 | $3,000,000.00 (paid) |
|  | - Evidence that completion of scheduled stages/deliverables is in accordance with the agreed four-year Project Plan and the 2023-24 Annual Implementation Plan. - Commonwealth acceptance of: - reviewed and updated four-year Project Plan. - a 2024-25 Annual Implementation Plan detailing project scope, project schedule, communication plan, high level design plans and a risk management plan. | 25/08/2024 | $3,000,000.00 (paid) |
|  | - Evidence that completion of scheduled stages/deliverables is in accordance with the agreed four-year Project Plan and the 2024-25 Annual Implementation Plan. - Commonwealth acceptance of: - reviewed and updated four-year Project Plan. - a 2025-26 Annual Implementation Plan detailing project scope, project schedule, communication plan, high level design plans and a risk management plan. | 25/08/2025 | $3,000,000.00 (paid) |
|  | Final report detailing actual performance against all outstanding deliverables from the agreed four-year (2023 -2026) Project Plan for control of yellow crazy ants in the Wet Tropics. | 09/08/2026 | Nil |
|  | Commonwealth acceptance of: - A two-year (2026-2028) Project Plan for control of yellow crazy ants in the Wet Tropics. - A 2026-27 Annual Implementation Plan detailing project scope, project schedule, communication plan, high level design plan and risk management plan. | 25/10/2026 | $3,000,000.00 |
|  | - Evidence that completion of scheduled stages / deliverables is in accordance with the agreed two-year Project Plan and the 2026-27 Annual Implementation Plan. - Commonwealth acceptance of: - Reviewed and updated two-year Project Plan. - A 2027-28 Annual Implementation Plan detailing project scope, project schedule, communication plan, high level design plan and a risk management plan. | 27/08/2027 | $3,000,000.00 |
|  | Final report detailing evidence of completion of scheduled stages / deliverables is in accordance with the agreed two-year Project Plan and the 2027-28 Annual Implementation Plan | 11/08/2028 | Nil |